## Dashboard
The mine closed Q3 with 47kt of underground developed reserves at a grade of 1.81g/t equivalent to 2 months of production at an average mining rate of 23kt per month. These reserves primarily comprise production stopes on 3L and 4L, which are currently the main sources of underground ore. Several stopes are fully developed on 6L; however, these will only be recognised as developed reserves when they are accessible for hoisting once the Lobe Shaft is commissioned in November 2024. The medium-term projection of developed reserves up to the end of FY2025 is shown in Figure 5. | To achieve the forecated developed reserves, focus must remain on 6L with target to start on 7L and 8L in November 2024. The current average development rate needs to increase to 1,055 meters per month by January 2025. Key actions to be implemented by the development team include: a. Tracking and sampling of development on a daily basis b. Weekly survey of all development ends. c. Increasing the drill steel length to 2m for haulage drives to improve the advance per blast to 1.7m. d. Increasing the drill steel length to 1.8m for sublevels to improve the advance per blast to 1.5m.
Phase 3 Commissioning

## Monthly Reserve Generation
|  |  | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-03-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01
1L | 1L_W24_STP | Diluted_Stoping_Tonnes | 2025-06-01: 4776
1L | 1L_W24_STP | Au_dil | 2025-06-01: 0.52
1L | 1L_W27_STP | Diluted_Stoping_Tonnes | 2026-06-01: 13884
1L | 1L_W27_STP | Au_dil | 2026-06-01: 0.47
1L | 1L_W28_STP | Diluted_Stoping_Tonnes | 2026-09-01: 16402
1L | 1L_W28_STP | Au_dil | 2026-09-01: 0.36
1L | 1L_W30_STP | Diluted_Stoping_Tonnes | 2027-06-01: 4138
1L | 1L_W30_STP | Au_dil | 2027-06-01: 3.71
1L Total | 1L Total | Diluted_Stoping_Tonnes | 2025-06-01: 4776; 2026-06-01: 13884; 2026-09-01: 16402; 2027-06-01: 4138
1L Total | 1L Total | Au_dil | 2025-06-01: 0.52; 2026-06-01: 0.47; 2026-09-01: 0.36; 2027-06-01: 3.71
3L | 3L_E8_STP | Diluted_Stoping_Tonnes
3L | 3L_E8_STP | Au_dil
3L | 3L_W23_STP | Diluted_Stoping_Tonnes | 2024-11-01: 11200
3L | 3L_W23_STP | Au_dil | 2024-11-01: 2.55
3L | 3L_W24A_STP | Diluted_Stoping_Tonnes | 2024-12-01: 5143
3L | 3L_W24A_STP | Au_dil | 2024-12-01: 0.8
3L | 3L_W24B_STP | Diluted_Stoping_Tonnes | 2024-12-01: 7459
3L | 3L_W24B_STP | Au_dil | 2024-12-01: 1.72
3L | 3L_W26A_STP | Diluted_Stoping_Tonnes | 2025-06-01: 3243
3L | 3L_W26A_STP | Au_dil | 2025-06-01: 1.58
3L | 3L_W26B_STP | Diluted_Stoping_Tonnes | 2025-07-01: 3101
3L | 3L_W26B_STP | Au_dil | 2025-07-01: 2.2
3L | 3L_W28A_STP | Diluted_Stoping_Tonnes | 2025-08-01: 14789
3L | 3L_W28A_STP | Au_dil | 2025-08-01: 2.53
3L | 3L_W28B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 15215
3L | 3L_W28B_STP | Au_dil | 2025-09-01: 2.63
3L Total | 3L Total | Diluted_Stoping_Tonnes | 2024-10-01: 12055; 2024-11-01: 11200; 2024-12-01: 12602; 2025-06-01: 3243; 2025-07-01: 3101; 2025-08-01: 14789; 2025-09-01: 15215
3L Total | 3L Total | Au_dil | 2024-10-01: 3.11; 2024-11-01: 2.55; 2024-12-01: 1.35; 2025-06-01: 1.58; 2025-07-01: 2.2; 2025-08-01: 2.53; 2025-09-01: 2.63
4L | 4L_W10B_STP | Diluted_Stoping_Tonnes
4L | 4L_W10B_STP | Au_dil
4L | 4L_W11A_STP | Diluted_Stoping_Tonnes
4L | 4L_W11A_STP | Au_dil
4L | 4L_W11B_STP | Diluted_Stoping_Tonnes
4L | 4L_W11B_STP | Au_dil
4L | 4L_W13B_STP | Diluted_Stoping_Tonnes
4L | 4L_W13B_STP | Au_dil
4L | 4L_W14A_STP | Diluted_Stoping_Tonnes
4L | 4L_W14A_STP | Au_dil
4L | 4L_W14B_STP | Diluted_Stoping_Tonnes
4L | 4L_W14B_STP | Au_dil
4L | 4L_W15A_STP | Diluted_Stoping_Tonnes
4L | 4L_W15A_STP | Au_dil
4L | 4L_W15B_STP | Diluted_Stoping_Tonnes
4L | 4L_W15B_STP | Au_dil
4L | 4L_W15C_STP | Diluted_Stoping_Tonnes
4L | 4L_W15C_STP | Au_dil
4L | 4L_W16A_STP | Diluted_Stoping_Tonnes
4L | 4L_W16A_STP | Au_dil
4L | 4L_W16B_STP | Diluted_Stoping_Tonnes
4L | 4L_W16B_STP | Au_dil
4L | 4L_W16C_STP | Diluted_Stoping_Tonnes
4L | 4L_W16C_STP | Au_dil
4L | 4L_W18A_STP | Diluted_Stoping_Tonnes
4L | 4L_W18A_STP | Au_dil
4L | 4L_W18B_STP | Diluted_Stoping_Tonnes
4L | 4L_W18B_STP | Au_dil
4L | 4L_W23_STP | Diluted_Stoping_Tonnes | 2024-12-01: 8489
4L | 4L_W23_STP | Au_dil | 2024-12-01: 1.81
4L Total | 4L Total | Diluted_Stoping_Tonnes | 2024-12-01: 5456
4L Total | 4L Total | Au_dil | 2024-12-01: 1.68
5L | 5L_W10B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 4015
5L | 5L_W10B_STP | Au_dil | 2025-03-01: 3.33
5L | 5L_W11A_STP | Diluted_Stoping_Tonnes | 2025-03-01: 2470
5L | 5L_W11A_STP | Au_dil | 2025-03-01: 2.94
5L | 5L_W11B_STP | Diluted_Stoping_Tonnes | 2025-04-01: 2645
5L | 5L_W11B_STP | Au_dil | 2025-04-01: 1.89
5L | 5L_W16A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 5190
5L | 5L_W16A_STP | Au_dil | 2025-10-01: 1.6
5L | 5L_W16B_STP | Diluted_Stoping_Tonnes | 2025-12-01: 4902
5L | 5L_W16B_STP | Au_dil | 2025-12-01: 1.4
5L | 5L_W18A_STP | Diluted_Stoping_Tonnes | 2025-12-01: 5174
5L | 5L_W18A_STP | Au_dil | 2025-12-01: 3.28
5L | 5L_W18B_STP | Diluted_Stoping_Tonnes | 2026-01-01: 5058
5L | 5L_W18B_STP | Au_dil | 2026-01-01: 2.8
5L | 5L_W25A_STP | Diluted_Stoping_Tonnes | 2025-07-01: 4877
5L | 5L_W25A_STP | Au_dil | 2025-07-01: 3.23
5L | 5L_W25B_STP | Diluted_Stoping_Tonnes | 2025-08-01: 6422
5L | 5L_W25B_STP | Au_dil | 2025-08-01: 3.97
5L | 5L_W5A_STP | Diluted_Stoping_Tonnes | 2024-11-01: 2036
5L | 5L_W5A_STP | Au_dil | 2024-11-01: 1.82
5L | 5L_W5B_STP | Diluted_Stoping_Tonnes | 2024-11-01: 2060
5L | 5L_W5B_STP | Au_dil | 2024-11-01: 1.7
5L | 5L_W6A_STP | Diluted_Stoping_Tonnes | 2025-02-01: 1907
5L | 5L_W6A_STP | Au_dil | 2025-02-01: 0.82
5L | 5L_W6B_STP | Diluted_Stoping_Tonnes | 2025-01-01: 1908
5L | 5L_W6B_STP | Au_dil | 2025-01-01: 0.92
5L | 5L_W7A_STP | Diluted_Stoping_Tonnes | 2025-01-01: 2958
5L | 5L_W7A_STP | Au_dil | 2025-01-01: 0.53
5L | 5L_W7B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 2940
5L | 5L_W7B_STP | Au_dil | 2025-03-01: 0.69
5L | 5L_W8A_STP | Diluted_Stoping_Tonnes | 2025-01-01: 4753
5L | 5L_W8A_STP | Au_dil | 2025-01-01: 3.3
5L | 5L_W8B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 4495
5L | 5L_W8B_STP | Au_dil | 2025-03-01: 3.97
5L Total | 5L Total | Diluted_Stoping_Tonnes | 2024-11-01: 4096; 2025-01-01: 9620; 2025-02-01: 1907; 2025-03-01: 13920; 2025-04-01: 2645; 2025-07-01: 4877; 2025-08-01: 6422; 2025-10-01: 5190; 2025-12-01: 10076; 2026-01-01: 5058
5L Total | 5L Total | Au_dil | 2024-11-01: 1.76; 2025-01-01: 1.98; 2025-02-01: 0.82; 2025-03-01: 2.91; 2025-04-01: 1.89; 2025-07-01: 3.23; 2025-08-01: 3.97; 2025-10-01: 1.6; 2025-12-01: 2.36; 2026-01-01: 2.8
6L | 6L_E1_STP | Diluted_Stoping_Tonnes | 2024-12-01: 42627
6L | 6L_E1_STP | Au_dil | 2024-12-01: 2.83
6L | 6L_W13_STP | Diluted_Stoping_Tonnes | 2024-12-01: 2154
6L | 6L_W13_STP | Au_dil | 2024-12-01: 3.63
6L | 6L_W14A_STP | Diluted_Stoping_Tonnes | 2024-12-01: 4226
6L | 6L_W14A_STP | Au_dil | 2024-12-01: 2.87
6L | 6L_W14B_STP | Diluted_Stoping_Tonnes | 2024-12-01: 4322
6L | 6L_W14B_STP | Au_dil | 2024-12-01: 2.45
6L | 6L_W19A_STP | Diluted_Stoping_Tonnes | 2025-05-01: 4755
6L | 6L_W19A_STP | Au_dil | 2025-05-01: 2.84
6L | 6L_W19B_STP | Diluted_Stoping_Tonnes | 2025-06-01: 5866
6L | 6L_W19B_STP | Au_dil | 2025-06-01: 3.2
6L | 6L_W2_STP | Diluted_Stoping_Tonnes | 2025-03-01: 29043
6L | 6L_W2_STP | Au_dil | 2025-03-01: 2.31
6L | 6L_W27_STP | Diluted_Stoping_Tonnes | 2025-05-01: 1166
6L | 6L_W27_STP | Au_dil | 2025-05-01: 3.97
6L | 6L_W28_STP | Diluted_Stoping_Tonnes | 2025-04-01: 635
6L | 6L_W28_STP | Au_dil | 2025-04-01: 2.85
6L | 6L_W4_STP | Diluted_Stoping_Tonnes | 2025-03-01: 10141
6L | 6L_W4_STP | Au_dil | 2025-03-01: 2.41
6L | 6L_W6_STP | Diluted_Stoping_Tonnes | 2024-12-01: 6279
6L | 6L_W6_STP | Au_dil | 2024-12-01: 2.17
6L | 6L_W8_STP | Diluted_Stoping_Tonnes | 2024-12-01: 2706
6L | 6L_W8_STP | Au_dil | 2024-12-01: 1.57
6L | 6L_W9_STP | Diluted_Stoping_Tonnes | 2024-12-01: 4690
6L | 6L_W9_STP | Au_dil | 2024-12-01: 2.7
6L Total | 6L Total | Diluted_Stoping_Tonnes | 2024-12-01: 67004; 2025-03-01: 39184; 2025-04-01: 635; 2025-05-01: 5921; 2025-06-01: 5866
6L Total | 6L Total | Au_dil | 2024-12-01: 2.71; 2025-03-01: 2.34; 2025-04-01: 2.85; 2025-05-01: 3.06; 2025-06-01: 3.2
6L_A | 6L_A_E4_STP | Diluted_Stoping_Tonnes | 2025-12-01: 2831
6L_A | 6L_A_E4_STP | Au_dil | 2025-12-01: 1.94
6L_A | 6L_A_E5_STP | Diluted_Stoping_Tonnes | 2026-03-01: 3272
6L_A | 6L_A_E5_STP | Au_dil | 2026-03-01: 3.22
6L_A | 6L_A_W11_STP | Diluted_Stoping_Tonnes | 2025-06-01: 894
6L_A | 6L_A_W11_STP | Au_dil | 2025-06-01: 3.05
6L_A | 6L_A_W12_STP | Diluted_Stoping_Tonnes | 2025-03-01: 2043
6L_A | 6L_A_W12_STP | Au_dil | 2025-03-01: 2.01
6L_A | 6L_A_W14_STP | Diluted_Stoping_Tonnes | 2025-05-01: 2171
6L_A | 6L_A_W14_STP | Au_dil | 2025-05-01: 1.64
6L_A | 6L_A_W19_STP | Diluted_Stoping_Tonnes | 2025-05-01: 3112
6L_A | 6L_A_W19_STP | Au_dil | 2025-05-01: 3.97
6L_A | 6L_A_W2_STP | Diluted_Stoping_Tonnes | 2025-10-01: 15923
6L_A | 6L_A_W2_STP | Au_dil | 2025-10-01: 2.17
6L_A | 6L_A_W26_STP | Diluted_Stoping_Tonnes | 2025-07-01: 1961
6L_A | 6L_A_W26_STP | Au_dil | 2025-07-01: 1.55
6L_A | 6L_A_W4_STP | Diluted_Stoping_Tonnes | 2025-07-01: 2610
6L_A | 6L_A_W4_STP | Au_dil | 2025-07-01: 3.49
6L_A | 6L_A_W6_STP | Diluted_Stoping_Tonnes | 2025-05-01: 2284
6L_A | 6L_A_W6_STP | Au_dil | 2025-05-01: 1.03
6L_A | 6L_A_W8_STP | Diluted_Stoping_Tonnes | 2025-07-01: 10047
6L_A | 6L_A_W8_STP | Au_dil | 2025-07-01: 2.45
6L_A Total | 6L_A Total | Diluted_Stoping_Tonnes | 2025-03-01: 2043; 2025-05-01: 7567; 2025-06-01: 894; 2025-07-01: 14618; 2025-10-01: 15923; 2025-12-01: 2831; 2026-03-01: 3272
6L_A Total | 6L_A Total | Au_dil | 2025-03-01: 2.01; 2025-05-01: 2.41; 2025-06-01: 3.05; 2025-07-01: 2.51; 2025-10-01: 2.17; 2025-12-01: 1.94; 2026-03-01: 3.22
7L | 7L_W10A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3173
7L | 7L_W10A_STP | Au_dil | 2025-09-01: 1.34
7L | 7L_W10B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3821
7L | 7L_W10B_STP | Au_dil | 2025-09-01: 3.12
7L | 7L_W14A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3908
7L | 7L_W14A_STP | Au_dil | 2025-09-01: 1.91
7L | 7L_W14B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3605
7L | 7L_W14B_STP | Au_dil | 2025-09-01: 2.88
7L | 7L_W18A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 5121
7L | 7L_W18A_STP | Au_dil | 2025-09-01: 3.61
7L | 7L_W18B_STP | Diluted_Stoping_Tonnes | 2025-10-01: 5305
7L | 7L_W18B_STP | Au_dil | 2025-10-01: 2.87
7L | 7L_W1B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 20536
7L | 7L_W1B_STP | Au_dil | 2025-09-01: 2.43
7L | 7L_W20A_STP | Diluted_Stoping_Tonnes | 2025-11-01: 1983
7L | 7L_W20A_STP | Au_dil | 2025-11-01: 3.97
7L | 7L_W20B_STP | Diluted_Stoping_Tonnes | 2025-12-01: 2679
7L | 7L_W20B_STP | Au_dil | 2025-12-01: 3.97
7L | 7L_W22A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 4263
7L | 7L_W22A_STP | Au_dil | 2026-01-01: 2.53
7L | 7L_W22B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 4258
7L | 7L_W22B_STP | Au_dil | 2026-02-01: 3.5
7L | 7L_W6_STP | Diluted_Stoping_Tonnes | 2025-09-01: 21485
7L | 7L_W6_STP | Au_dil | 2025-09-01: 2.16
7L Total | 7L Total | Diluted_Stoping_Tonnes | 2025-09-01: 61649; 2025-10-01: 5305; 2025-11-01: 1983; 2025-12-01: 2679; 2026-01-01: 4263; 2026-02-01: 4258
7L Total | 7L Total | Au_dil | 2025-09-01: 2.42; 2025-10-01: 2.87; 2025-11-01: 3.97; 2025-12-01: 3.97; 2026-01-01: 2.53; 2026-02-01: 3.5
8L | 8L_E5A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 5483
8L | 8L_E5A_STP | Au_dil | 2025-09-01: 2.24
8L | 8L_E5B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 4846
8L | 8L_E5B_STP | Au_dil | 2025-09-01: 2.64
8L | 8L_W10A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3303
8L | 8L_W10A_STP | Au_dil | 2025-09-01: 3.97
8L | 8L_W10B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3570
8L | 8L_W10B_STP | Au_dil | 2025-09-01: 2.55
8L | 8L_W14A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3959
8L | 8L_W14A_STP | Au_dil | 2025-09-01: 3.97
8L | 8L_W14B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 4267
8L | 8L_W14B_STP | Au_dil | 2025-09-01: 2.23
8L | 8L_W16A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3202
8L | 8L_W16A_STP | Au_dil | 2025-09-01: 2.94
8L | 8L_W16B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 3321
8L | 8L_W16B_STP | Au_dil | 2025-09-01: 2.36
8L | 8L_W18A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 4154
8L | 8L_W18A_STP | Au_dil | 2025-09-01: 3.08
8L | 8L_W18B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 4448
8L | 8L_W18B_STP | Au_dil | 2025-09-01: 3.6
8L | 8L_W20A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 1556
8L | 8L_W20A_STP | Au_dil | 2025-10-01: 2.85
8L | 8L_W20B_STP | Diluted_Stoping_Tonnes | 2025-10-01: 1606
8L | 8L_W20B_STP | Au_dil | 2025-10-01: 2.73
8L | 8L_W22A_STP | Diluted_Stoping_Tonnes | 2025-12-01: 4610
8L | 8L_W22A_STP | Au_dil | 2025-12-01: 2.73
8L | 8L_W22B_STP | Diluted_Stoping_Tonnes | 2026-01-01: 5076
8L | 8L_W22B_STP | Au_dil | 2026-01-01: 2.74
8L | 8L_W24A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 4619
8L | 8L_W24A_STP | Au_dil | 2026-01-01: 3.75
8L | 8L_W24B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 3950; 2026-03-01: 1863
8L | 8L_W24B_STP | Au_dil | 2026-02-01: 3.66; 2026-03-01: 3.66
8L | 8L_W7A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 842
8L | 8L_W7A_STP | Au_dil | 2025-10-01: 3.44
8L | 8L_W7B_STP | Diluted_Stoping_Tonnes | 2025-12-01: 602
8L | 8L_W7B_STP | Au_dil | 2025-12-01: 2.88
8L Total | 8L Total | Diluted_Stoping_Tonnes | 2025-09-01: 40552; 2025-10-01: 4005; 2025-12-01: 5212; 2026-01-01: 9695; 2026-02-01: 3950; 2026-03-01: 1863
8L Total | 8L Total | Au_dil | 2025-09-01: 2.92; 2025-10-01: 2.92; 2025-12-01: 2.75; 2026-01-01: 3.22; 2026-02-01: 3.66; 2026-03-01: 3.66
9L | 9L_E5_STP | Diluted_Stoping_Tonnes | 2026-02-01: 5985
9L | 9L_E5_STP | Au_dil | 2026-02-01: 1.99
9L | 9L_E9_STP | Diluted_Stoping_Tonnes | 2026-02-01: 2494
9L | 9L_E9_STP | Au_dil | 2026-02-01: 2.29
9L | 9L_W1_STP | Diluted_Stoping_Tonnes | 2026-04-01: 35788
9L | 9L_W1_STP | Au_dil | 2026-04-01: 1.8
9L | 9L_W16A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 2818
9L | 9L_W16A_STP | Au_dil | 2026-01-01: 2.46
9L | 9L_W16B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 3022
9L | 9L_W16B_STP | Au_dil | 2026-02-01: 2.68
9L | 9L_W18A_STP | Diluted_Stoping_Tonnes | 2026-03-01: 3048; 2026-04-01: 223
9L | 9L_W18A_STP | Au_dil | 2026-03-01: 3.97; 2026-04-01: 3.97
9L | 9L_W18B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 3662
9L | 9L_W18B_STP | Au_dil | 2026-04-01: 3.97
9L | 9L_W20A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 2403
9L | 9L_W20A_STP | Au_dil | 2026-04-01: 3.53
9L | 9L_W20B_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1964
9L | 9L_W20B_STP | Au_dil | 2026-05-01: 3.2
9L | 9L_W22A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 3624
9L | 9L_W22A_STP | Au_dil | 2026-04-01: 3.01
9L | 9L_W22B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 4093
9L | 9L_W22B_STP | Au_dil | 2026-04-01: 2.45
9L | 9L_W24_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1126
9L | 9L_W24_STP | Au_dil | 2026-05-01: 1.97
9L | 9L_W4_STP | Diluted_Stoping_Tonnes | 2026-04-01: 17674
9L | 9L_W4_STP | Au_dil | 2026-04-01: 1.92
9L | 9L_W6A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 2955
9L | 9L_W6A_STP | Au_dil | 2026-04-01: 3.97
9L | 9L_W6B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1886
9L | 9L_W6B_STP | Au_dil | 2026-06-01: 3.79
9L Total | 9L Total | Diluted_Stoping_Tonnes | 2026-01-01: 2818; 2026-02-01: 11501; 2026-03-01: 3048; 2026-04-01: 70422; 2026-05-01: 3090; 2026-06-01: 1886
9L Total | 9L Total | Au_dil | 2026-01-01: 2.46; 2026-02-01: 2.24; 2026-03-01: 3.97; 2026-04-01: 2.2; 2026-05-01: 2.76; 2026-06-01: 3.79
10L | 10L_E1A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 4158
10L | 10L_E1A_STP | Au_dil | 2026-02-01: 3
10L | 10L_E1B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 2613
10L | 10L_E1B_STP | Au_dil | 2026-02-01: 2.95
10L | 10L_E7A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 3917
10L | 10L_E7A_STP | Au_dil | 2026-06-01: 3.97
10L | 10L_E7B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 3495
10L | 10L_E7B_STP | Au_dil | 2026-07-01: 3.97
10L | 10L_E9_STP | Diluted_Stoping_Tonnes | 2026-07-01: 1470
10L | 10L_E9_STP | Au_dil | 2026-07-01: 3.97
10L | 10L_W16A_STP | Diluted_Stoping_Tonnes | 2025-12-01: 2532
10L | 10L_W16A_STP | Au_dil | 2025-12-01: 3.21
10L | 10L_W16B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 2361
10L | 10L_W16B_STP | Au_dil | 2026-02-01: 3.67
10L | 10L_W18A_STP | Diluted_Stoping_Tonnes | 2025-12-01: 2488
10L | 10L_W18A_STP | Au_dil | 2025-12-01: 3.97
10L | 10L_W18B_STP | Diluted_Stoping_Tonnes | 2025-12-01: 2516
10L | 10L_W18B_STP | Au_dil | 2025-12-01: 3.97
10L | 10L_W1A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 31474
10L | 10L_W1A_STP | Au_dil | 2026-02-01: 2.26
10L | 10L_W1B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 27138
10L | 10L_W1B_STP | Au_dil | 2026-02-01: 2.12
10L | 10L_W20A_STP | Diluted_Stoping_Tonnes | 2026-05-01: 3171
10L | 10L_W20A_STP | Au_dil | 2026-05-01: 3.97
10L | 10L_W20B_STP | Diluted_Stoping_Tonnes | 2026-05-01: 2720
10L | 10L_W20B_STP | Au_dil | 2026-05-01: 3.58
10L | 10L_W22A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1204
10L | 10L_W22A_STP | Au_dil | 2026-06-01: 1.79
10L | 10L_W22B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 2106
10L | 10L_W22B_STP | Au_dil | 2026-06-01: 2.49
10L | 10L_W4A_STP | Diluted_Stoping_Tonnes | 2026-05-01: 15313
10L | 10L_W4A_STP | Au_dil | 2026-05-01: 2.02
10L | 10L_W4B_STP | Diluted_Stoping_Tonnes | 2026-05-01: 13457
10L | 10L_W4B_STP | Au_dil | 2026-05-01: 2.12
10L | 10L_W6A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 5968
10L | 10L_W6A_STP | Au_dil | 2026-06-01: 3.97
10L | 10L_W6B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 4245
10L | 10L_W6B_STP | Au_dil | 2026-07-01: 3.97
10L | 10L_W8A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 5081
10L | 10L_W8A_STP | Au_dil | 2026-06-01: 3.05
10L | 10L_W8B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 5373
10L | 10L_W8B_STP | Au_dil | 2026-06-01: 3.97
10L Total | 10L Total | Diluted_Stoping_Tonnes | 2025-12-01: 7536; 2026-02-01: 67746; 2026-05-01: 34661; 2026-06-01: 23649; 2026-07-01: 9210
10L Total | 10L Total | Au_dil | 2025-12-01: 3.72; 2026-02-01: 2.33; 2026-05-01: 2.36; 2026-06-01: 3.53; 2026-07-01: 3.97
11L | 11L_E1A_STP | Diluted_Stoping_Tonnes | 2026-09-01: 11391
11L | 11L_E1A_STP | Au_dil | 2026-09-01: 2.77
11L | 11L_E1B_STP | Diluted_Stoping_Tonnes | 2026-10-01: 9509
11L | 11L_E1B_STP | Au_dil | 2026-10-01: 3.19
11L | 11L_E7A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 5761
11L | 11L_E7A_STP | Au_dil | 2026-08-01: 1.14
11L | 11L_E7B_STP | Diluted_Stoping_Tonnes | 2026-10-01: 8394
11L | 11L_E7B_STP | Au_dil | 2026-10-01: 2.46
11L | 11L_W10A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 11213
11L | 11L_W10A_STP | Au_dil | 2026-08-01: 1.95
11L | 11L_W10B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 16649
11L | 11L_W10B_STP | Au_dil | 2026-08-01: 1.94
11L | 11L_W14A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 4973
11L | 11L_W14A_STP | Au_dil | 2026-08-01: 1.83
11L | 11L_W14B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 4143
11L | 11L_W14B_STP | Au_dil | 2026-08-01: 1.93
11L | 11L_W18A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 3361
11L | 11L_W18A_STP | Au_dil | 2026-08-01: 3.76
11L | 11L_W18B_STP | Diluted_Stoping_Tonnes | 2026-10-01: 4345
11L | 11L_W18B_STP | Au_dil | 2026-10-01: 3.21
11L | 11L_W4A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 7095
11L | 11L_W4A_STP | Au_dil | 2026-08-01: 3.93
11L | 11L_W4B_STP | Diluted_Stoping_Tonnes | 2026-09-01: 7302
11L | 11L_W4B_STP | Au_dil | 2026-09-01: 3.72
11L | 11L_W6A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1790
11L | 11L_W6A_STP | Au_dil | 2026-08-01: 2.4
11L | 11L_W6B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 2519
11L | 11L_W6B_STP | Au_dil | 2026-08-01: 1.99
11L | 11L_W9_STP | Diluted_Stoping_Tonnes | 2026-08-01: 4327
11L | 11L_W9_STP | Au_dil | 2026-08-01: 1.8
11L Total | 11L Total | Diluted_Stoping_Tonnes | 2026-08-01: 61830; 2026-09-01: 18694; 2026-10-01: 22248
11L Total | 11L Total | Au_dil | 2026-08-01: 2.19; 2026-09-01: 3.14; 2026-10-01: 2.92
11L_A | 11L_A_E1A_STP | Diluted_Stoping_Tonnes | 2026-10-01: 5063
11L_A | 11L_A_E1A_STP | Au_dil | 2026-10-01: 2.91
11L_A | 11L_A_E1B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 4819
11L_A | 11L_A_E1B_STP | Au_dil | 2026-12-01: 3.39
11L_A | 11L_A_W17A_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1742
11L_A | 11L_A_W17A_STP | Au_dil | 2026-09-01: 2.87
11L_A | 11L_A_W17B_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1659
11L_A | 11L_A_W17B_STP | Au_dil | 2026-09-01: 3.97
11L_A | 11L_A_W18A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 3319
11L_A | 11L_A_W18A_STP | Au_dil | 2026-11-01: 3.97
11L_A | 11L_A_W18B_STP | Diluted_Stoping_Tonnes | 2026-11-01: 2914
11L_A | 11L_A_W18B_STP | Au_dil | 2026-11-01: 3.97
11L_A | 11L_A_W20A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1678
11L_A | 11L_A_W20A_STP | Au_dil | 2026-11-01: 3.66
11L_A | 11L_A_W20B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 2763
11L_A | 11L_A_W20B_STP | Au_dil | 2026-12-01: 3.97
11L_A | 11L_A_W3A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 3258
11L_A | 11L_A_W3A_STP | Au_dil | 2026-11-01: 3.97
11L_A | 11L_A_W3B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1842
11L_A | 11L_A_W3B_STP | Au_dil | 2026-12-01: 3.97
11L_A | 11L_A_W5A_STP | Diluted_Stoping_Tonnes | 2026-10-01: 2654
11L_A | 11L_A_W5A_STP | Au_dil | 2026-10-01: 2.17
11L_A | 11L_A_W8A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 3480
11L_A | 11L_A_W8A_STP | Au_dil | 2026-11-01: 2.22
11L_A | 11L_A_W8B_STP | Diluted_Stoping_Tonnes | 2026-11-01: 4717
11L_A | 11L_A_W8B_STP | Au_dil | 2026-11-01: 2.87
11L_A Total | 11L_A Total | Diluted_Stoping_Tonnes | 2026-09-01: 3401; 2026-10-01: 7717; 2026-11-01: 19367; 2026-12-01: 9424
11L_A Total | 11L_A Total | Au_dil | 2026-09-01: 3.41; 2026-10-01: 2.65; 2026-11-01: 3.36; 2026-12-01: 3.67
12L | 12L_W10A_STP | Diluted_Stoping_Tonnes | 2027-01-01: 4695
12L | 12L_W10A_STP | Au_dil | 2027-01-01: 2.3
12L | 12L_W10B_STP | Diluted_Stoping_Tonnes | 2027-01-01: 5156
12L | 12L_W10B_STP | Au_dil | 2027-01-01: 3.65
12L | 12L_W12A_STP | Diluted_Stoping_Tonnes | 2026-12-01: 2821
12L | 12L_W12A_STP | Au_dil | 2026-12-01: 3.18
12L | 12L_W12B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 3622
12L | 12L_W12B_STP | Au_dil | 2026-12-01: 2.09
12L | 12L_W15A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 508; 2026-12-01: 508
12L | 12L_W15A_STP | Au_dil | 2026-11-01: 2.9; 2026-12-01: 2.9
12L | 12L_W15B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1692
12L | 12L_W15B_STP | Au_dil | 2026-12-01: 2.77
12L | 12L_W16A_STP | Diluted_Stoping_Tonnes | 2027-01-01: 3965
12L | 12L_W16A_STP | Au_dil | 2027-01-01: 1.85
12L | 12L_W16B_STP | Diluted_Stoping_Tonnes | 2027-01-01: 5256
12L | 12L_W16B_STP | Au_dil | 2027-01-01: 3.97
12L | 12L_W18_STP | Diluted_Stoping_Tonnes | 2027-01-01: 963
12L | 12L_W18_STP | Au_dil | 2027-01-01: 3.5
12L | 12L_W1A_STP | Diluted_Stoping_Tonnes | 2026-12-01: 2794
12L | 12L_W1A_STP | Au_dil | 2026-12-01: 3.97
12L | 12L_W1B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 3592
12L | 12L_W1B_STP | Au_dil | 2026-12-01: 1.88
12L | 12L_W3A_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1432
12L | 12L_W3A_STP | Au_dil | 2026-12-01: 3.97
12L | 12L_W3B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 2565
12L | 12L_W3B_STP | Au_dil | 2026-12-01: 3.97
12L | 12L_W5A_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1962
12L | 12L_W5A_STP | Au_dil | 2026-12-01: 3.89
12L | 12L_W5B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 2012
12L | 12L_W5B_STP | Au_dil | 2026-12-01: 3.43
12L | 12L_W9A_STP | Diluted_Stoping_Tonnes | 2027-01-01: 1015
12L | 12L_W9A_STP | Au_dil | 2027-01-01: 3.03
12L | 12L_W9B_STP | Diluted_Stoping_Tonnes | 2027-01-01: 1886
12L | 12L_W9B_STP | Au_dil | 2027-01-01: 3.97
12L Total | 12L Total | Diluted_Stoping_Tonnes | 2026-11-01: 508; 2026-12-01: 23000; 2027-01-01: 22936
12L Total | 12L Total | Au_dil | 2026-11-01: 2.9; 2026-12-01: 3.09; 2027-01-01: 3.13
12L_A | 12L_A_E1_STP | Diluted_Stoping_Tonnes | 2027-03-01: 9732
12L_A | 12L_A_E1_STP | Au_dil | 2027-03-01: 2.19
12L_A | 12L_A_W1_STP | Diluted_Stoping_Tonnes | 2027-01-01: 2083
12L_A | 12L_A_W1_STP | Au_dil | 2027-01-01: 3.97
12L_A | 12L_A_W11A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 973
12L_A | 12L_A_W11A_STP | Au_dil | 2027-07-01: 2.47
12L_A | 12L_A_W11B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1910
12L_A | 12L_A_W11B_STP | Au_dil | 2027-07-01: 2.26
12L_A | 12L_A_W12A_STP | Diluted_Stoping_Tonnes | 2027-08-01: 3268
12L_A | 12L_A_W12A_STP | Au_dil | 2027-08-01: 2.2
12L_A | 12L_A_W12B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 4139
12L_A | 12L_A_W12B_STP | Au_dil | 2027-09-01: 1.73
12L_A | 12L_A_W14A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 3398
12L_A | 12L_A_W14A_STP | Au_dil | 2027-09-01: 2.41
12L_A | 12L_A_W14B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 3792
12L_A | 12L_A_W14B_STP | Au_dil | 2027-09-01: 2.25
12L_A | 12L_A_W18A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 527
12L_A | 12L_A_W18A_STP | Au_dil | 2027-09-01: 2.6
12L_A | 12L_A_W18B_STP | Diluted_Stoping_Tonnes | 2027-11-01: 621
12L_A | 12L_A_W18B_STP | Au_dil | 2027-11-01: 1.79
12L_A | 12L_A_W4A_STP | Diluted_Stoping_Tonnes | 2027-03-01: 5015
12L_A | 12L_A_W4A_STP | Au_dil | 2027-03-01: 3.02
12L_A | 12L_A_W4B_STP | Diluted_Stoping_Tonnes | 2027-03-01: 5257
12L_A | 12L_A_W4B_STP | Au_dil | 2027-03-01: 2.9
12L_A | 12L_A_W5_STP | Diluted_Stoping_Tonnes | 2027-03-01: 734
12L_A | 12L_A_W5_STP | Au_dil | 2027-03-01: 3.27
12L_A | 12L_A_W6_STP | Diluted_Stoping_Tonnes | 2027-05-01: 4417
12L_A | 12L_A_W6_STP | Au_dil | 2027-05-01: 3.84
12L_A Total | 12L_A Total | Diluted_Stoping_Tonnes | 2027-01-01: 2083; 2027-03-01: 20739; 2027-05-01: 4417; 2027-07-01: 2884; 2027-08-01: 3268; 2027-09-01: 11857; 2027-11-01: 621
12L_A Total | 12L_A Total | Au_dil | 2027-01-01: 3.97; 2027-03-01: 2.61; 2027-05-01: 3.84; 2027-07-01: 2.33; 2027-08-01: 2.2; 2027-09-01: 2.13; 2027-11-01: 1.79
13L | 13L_E1A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 21435
13L | 13L_E1A_STP | Au_dil | 2027-07-01: 2.09
13L | 13L_E1B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 22805
13L | 13L_E1B_STP | Au_dil | 2027-06-01: 2.42
13L | 13L_W10_STP | Diluted_Stoping_Tonnes | 2027-06-01: 3629
13L | 13L_W10_STP | Au_dil | 2027-06-01: 3.97
13L | 13L_W12_STP | Diluted_Stoping_Tonnes | 2027-06-01: 4238
13L | 13L_W12_STP | Au_dil | 2027-06-01: 2.14
13L | 13L_W1A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 6219
13L | 13L_W1A_STP | Au_dil | 2027-06-01: 3.7
13L | 13L_W1B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 5043
13L | 13L_W1B_STP | Au_dil | 2027-06-01: 3.97
13L | 13L_W4A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 6532
13L | 13L_W4A_STP | Au_dil | 2027-06-01: 2.08
13L | 13L_W4B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 5841
13L | 13L_W4B_STP | Au_dil | 2027-06-01: 1.91
13L | 13L_W6A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1748
13L | 13L_W6A_STP | Au_dil | 2027-06-01: 2.33
13L | 13L_W6B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 2450
13L | 13L_W6B_STP | Au_dil | 2027-06-01: 2.95
13L | 13L_W8A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1702
13L | 13L_W8A_STP | Au_dil | 2027-06-01: 3.83
13L | 13L_W8B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1350
13L | 13L_W8B_STP | Au_dil | 2027-06-01: 2.93
13L | 13L_W9_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1727
13L | 13L_W9_STP | Au_dil | 2027-06-01: 2.1
13L Total | 13L Total | Diluted_Stoping_Tonnes | 2027-06-01: 63283; 2027-07-01: 21435
13L Total | 13L Total | Au_dil | 2027-06-01: 2.72; 2027-07-01: 2.09
13L_A | 13L_A_E1A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 17277
13L_A | 13L_A_E1A_STP | Au_dil | 2027-06-01: 3.34
13L_A | 13L_A_E1B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 14279
13L_A | 13L_A_E1B_STP | Au_dil | 2027-06-01: 3.97
13L_A | 13L_A_E4A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 7464
13L_A | 13L_A_E4A_STP | Au_dil | 2027-06-01: 2.69
13L_A | 13L_A_E4B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 7025
13L_A | 13L_A_E4B_STP | Au_dil | 2027-06-01: 3.31
13L_A | 13L_A_E5A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 767
13L_A | 13L_A_E5A_STP | Au_dil | 2027-06-01: 3.59
13L_A | 13L_A_E5B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1835
13L_A | 13L_A_E5B_STP | Au_dil | 2027-07-01: 3.51
13L_A | 13L_A_W10A_STP | Diluted_Stoping_Tonnes | 2027-10-01: 4309
13L_A | 13L_A_W10A_STP | Au_dil | 2027-10-01: 1.66
13L_A | 13L_A_W10B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 5188
13L_A | 13L_A_W10B_STP | Au_dil | 2027-10-01: 2.03
13L_A | 13L_A_W12A_STP | Diluted_Stoping_Tonnes | 2027-08-01: 4897
13L_A | 13L_A_W12A_STP | Au_dil | 2027-08-01: 3.03
13L_A | 13L_A_W12B_STP | Diluted_Stoping_Tonnes | 2027-08-01: 4776
13L_A | 13L_A_W12B_STP | Au_dil | 2027-08-01: 2.94
13L_A | 13L_A_W14A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 3020
13L_A | 13L_A_W14A_STP | Au_dil | 2027-09-01: 3.8
13L_A | 13L_A_W14B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 2490
13L_A | 13L_A_W14B_STP | Au_dil | 2027-09-01: 3.6
13L_A | 13L_A_W16A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1324
13L_A | 13L_A_W16A_STP | Au_dil | 2027-09-01: 3.48
13L_A | 13L_A_W16B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 3249
13L_A | 13L_A_W16B_STP | Au_dil | 2027-10-01: 2.42
13L_A | 13L_A_W1A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 7533
13L_A | 13L_A_W1A_STP | Au_dil | 2027-06-01: 3.72
13L_A | 13L_A_W1B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 6924
13L_A | 13L_A_W1B_STP | Au_dil | 2027-06-01: 3.33
13L_A | 13L_A_W6A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 3227
13L_A | 13L_A_W6A_STP | Au_dil | 2027-06-01: 3.97
13L_A | 13L_A_W6B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 3052
13L_A | 13L_A_W6B_STP | Au_dil | 2027-06-01: 3.97
13L_A | 13L_A_W8_STP | Diluted_Stoping_Tonnes | 2027-08-01: 2653
13L_A | 13L_A_W8_STP | Au_dil | 2027-08-01: 3.97
13L_A | 13L_A_W9_STP | Diluted_Stoping_Tonnes | 2027-06-01: 2616
13L_A | 13L_A_W9_STP | Au_dil | 2027-06-01: 3.97
13L_A Total | 13L_A Total | Diluted_Stoping_Tonnes | 2027-06-01: 70163; 2027-07-01: 1835; 2027-08-01: 12326; 2027-09-01: 6833; 2027-10-01: 12747
13L_A Total | 13L_A Total | Au_dil | 2027-06-01: 3.52; 2027-07-01: 3.51; 2027-08-01: 3.2; 2027-09-01: 3.66; 2027-10-01: 2
14L | 14L_W1A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 4168
14L | 14L_W1A_STP | Au_dil | 2027-09-01: 3.59
14L | 14L_W1B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 4764
14L | 14L_W1B_STP | Au_dil | 2027-09-01: 3.6
14L | 14L_W8A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 2274
14L | 14L_W8A_STP | Au_dil | 2027-06-01: 3.97
14L | 14L_W8B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 2848
14L | 14L_W8B_STP | Au_dil | 2027-06-01: 3.97
14L Total | 14L Total | Diluted_Stoping_Tonnes | 2027-06-01: 5122; 2027-09-01: 8932
14L Total | 14L Total | Au_dil | 2027-06-01: 3.97; 2027-09-01: 3.59
14L_A | 14L_A_W1A_STP | Diluted_Stoping_Tonnes | 2027-10-01: 5705
14L_A | 14L_A_W1A_STP | Au_dil | 2027-10-01: 3.81
14L_A | 14L_A_W1B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 6045
14L_A | 14L_A_W1B_STP | Au_dil | 2027-09-01: 3.61
14L_A | 14L_A_W4A_STP | Diluted_Stoping_Tonnes | 2027-08-01: 6602
14L_A | 14L_A_W4A_STP | Au_dil | 2027-08-01: 1.86
14L_A | 14L_A_W4B_STP | Diluted_Stoping_Tonnes | 2027-08-01: 6736
14L_A | 14L_A_W4B_STP | Au_dil | 2027-08-01: 1.97
14L_A | 14L_A_W7A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 601
14L_A | 14L_A_W7A_STP | Au_dil | 2027-06-01: 3.97
14L_A | 14L_A_W7B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1203
14L_A | 14L_A_W7B_STP | Au_dil | 2027-07-01: 3.91
14L_A | 14L_A_W8A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 4389
14L_A | 14L_A_W8A_STP | Au_dil | 2027-06-01: 1.95
14L_A | 14L_A_W8B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 4841
14L_A | 14L_A_W8B_STP | Au_dil | 2027-06-01: 2.28
14L_A Total | 14L_A Total | Diluted_Stoping_Tonnes | 2027-06-01: 9831; 2027-07-01: 1203; 2027-08-01: 13337; 2027-09-01: 6045; 2027-10-01: 5705
14L_A Total | 14L_A Total | Au_dil | 2027-06-01: 2.24; 2027-07-01: 3.91; 2027-08-01: 1.92; 2027-09-01: 3.61; 2027-10-01: 3.81
15L | 15L_W1_STP | Diluted_Stoping_Tonnes | 2027-10-01: 5783
15L | 15L_W1_STP | Au_dil | 2027-10-01: 2.31
15L | 15L_W10_STP | Diluted_Stoping_Tonnes | 2027-06-01: 9962
15L | 15L_W10_STP | Au_dil | 2027-06-01: 3.97
15L | 15L_W8_STP | Diluted_Stoping_Tonnes | 2027-06-01: 2589
15L | 15L_W8_STP | Au_dil | 2027-06-01: 3.97
15L Total | 15L Total | Diluted_Stoping_Tonnes | 2027-06-01: 12550; 2027-10-01: 5783
15L Total | 15L Total | Au_dil | 2027-06-01: 3.97; 2027-10-01: 2.31
Grand Total | Grand Total | Diluted_Stoping_Tonnes | 20600 | 7214 | 19457 | 6842 | 59160 | 15296 | 85063 | 9620 | 1907 | 55147 | 3279 | 13488 | 14779 | 22596 | 21211 | 117416 | 30423 | 1983 | 28334 | 21834 | 87455 | 8183 | 70422 | 37751 | 39419 | 9210 | 61830 | 38497 | 29965 | 19875 | 32424 | 25018 | 20739 | 4417 | 165088 | 27357 | 28931 | 33667 | 24234 | 621
Grand Total | Grand Total | Au_dil | 1.75 | 2.07 | 1.4 | 0.96 | 2.2 | 2.34 | 2.44 | 1.98 | 0.82 | 2.47 | 2.08 | 2.7 | 1.97 | 2.62 | 2.97 | 2.62 | 2.29 | 3.97 | 2.9 | 2.89 | 2.43 | 3.6 | 2.2 | 2.39 | 2.46 | 3.97 | 2.19 | 1.98 | 2.85 | 3.35 | 3.26 | 3.2 | 2.61 | 3.84 | 3.19 | 2.29 | 2.5 | 3.1 | 2.5 | 1.79

## Stoping Schedule
 | time axis 2024-06-01 to 2028-10-01
1L | 1L_W24_STP | Diluted_Stoping_Tonnes | 2025-06-01: 1703; 2025-07-01: 2022; 2025-08-01: 1050
1L | 1L_W24_STP | Au_dil | 2025-06-01: 0.52; 2025-07-01: 0.52; 2025-08-01: 0.52
1L | 1L_W27_STP | Diluted_Stoping_Tonnes | 2026-06-01: 397; 2026-07-01: 3033; 2026-08-01: 2696; 2026-09-01: 2921; 2026-10-01: 3033; 2026-11-01: 1803
1L | 1L_W27_STP | Au_dil | 2026-06-01: 0.47; 2026-07-01: 0.47; 2026-08-01: 0.47; 2026-09-01: 0.47; 2026-10-01: 0.47; 2026-11-01: 0.47
1L | 1L_W28_STP | Diluted_Stoping_Tonnes | 2026-09-01: 352; 2026-10-01: 2022; 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1872; 2027-05-01: 1798; 2027-06-01: 1219
1L | 1L_W28_STP | Au_dil | 2026-09-01: 0.36; 2026-10-01: 0.36; 2026-11-01: 0.36; 2026-12-01: 0.36; 2027-01-01: 0.36; 2027-02-01: 0.36; 2027-03-01: 0.36; 2027-04-01: 0.36; 2027-05-01: 0.36; 2027-06-01: 0.36
1L | 1L_W30_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1150; 2027-07-01: 2022; 2027-08-01: 966
1L | 1L_W30_STP | Au_dil | 2027-06-01: 3.71; 2027-07-01: 3.71; 2027-08-01: 3.71
1L Total | 1L Total | Diluted_Stoping_Tonnes | 2025-06-01: 1703; 2025-07-01: 2022; 2025-08-01: 1050; 2026-06-01: 397; 2026-07-01: 3033; 2026-08-01: 2696; 2026-09-01: 3274; 2026-10-01: 5056; 2026-11-01: 3675; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1872; 2027-05-01: 1798; 2027-06-01: 2370; 2027-07-01: 2022; 2027-08-01: 966
1L Total | 1L Total | Au_dil | 2025-06-01: 0.52; 2025-07-01: 0.52; 2025-08-01: 0.52; 2026-06-01: 0.47; 2026-07-01: 0.47; 2026-08-01: 0.47; 2026-09-01: 0.45; 2026-10-01: 0.42; 2026-11-01: 0.41; 2026-12-01: 0.36; 2027-01-01: 0.36; 2027-02-01: 0.36; 2027-03-01: 0.36; 2027-04-01: 0.36; 2027-05-01: 0.36; 2027-06-01: 1.99; 2027-07-01: 3.71; 2027-08-01: 3.71
3L | 3L_E8_STP | Diluted_Stoping_Tonnes | 2024-10-01: 4045; 2024-11-01: 3895; 2024-12-01: 3595; 2025-01-01: 521
3L | 3L_E8_STP | Au_dil | 2024-10-01: 3.11; 2024-11-01: 3.11; 2024-12-01: 3.11; 2025-01-01: 3.11
3L | 3L_W23_STP | Diluted_Stoping_Tonnes | 2025-01-01: 658; 2025-02-01: 2696; 2025-03-01: 2921; 2025-04-01: 2584; 2025-05-01: 2341
3L | 3L_W23_STP | Au_dil | 2025-01-01: 2.55; 2025-02-01: 2.55; 2025-03-01: 2.55; 2025-04-01: 2.55; 2025-05-01: 2.55
3L | 3L_W24A_STP | Diluted_Stoping_Tonnes | 2025-02-01: 1700; 2025-03-01: 1947; 2025-04-01: 1496
3L | 3L_W24A_STP | Au_dil | 2025-02-01: 0.8; 2025-03-01: 0.8; 2025-04-01: 0.8
3L | 3L_W24B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 1947; 2025-04-01: 1723; 2025-05-01: 1798; 2025-06-01: 1872; 2025-07-01: 119
3L | 3L_W24B_STP | Au_dil | 2025-03-01: 1.72; 2025-04-01: 1.72; 2025-05-01: 1.72; 2025-06-01: 1.72; 2025-07-01: 1.72
3L | 3L_W26A_STP | Diluted_Stoping_Tonnes | 2025-08-01: 168; 2025-09-01: 2022; 2025-10-01: 1053
3L | 3L_W26A_STP | Au_dil | 2025-08-01: 1.58; 2025-09-01: 1.58; 2025-10-01: 1.58
3L | 3L_W26B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 258; 2025-10-01: 1798; 2025-11-01: 1046
3L | 3L_W26B_STP | Au_dil | 2025-09-01: 2.2; 2025-10-01: 2.2; 2025-11-01: 2.2
3L | 3L_W28A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 1346; 2025-11-01: 2921; 2025-12-01: 3033; 2026-01-01: 2809; 2026-02-01: 2696; 2026-03-01: 1983
3L | 3L_W28A_STP | Au_dil | 2025-10-01: 2.53; 2025-11-01: 2.53; 2025-12-01: 2.53; 2026-01-01: 2.53; 2026-02-01: 2.53; 2026-03-01: 2.53
3L | 3L_W28B_STP | Diluted_Stoping_Tonnes | 2025-11-01: 2332; 2025-12-01: 3033; 2026-01-01: 2809; 2026-02-01: 2696; 2026-03-01: 2921; 2026-04-01: 1423
3L | 3L_W28B_STP | Au_dil | 2025-11-01: 2.63; 2025-12-01: 2.63; 2026-01-01: 2.63; 2026-02-01: 2.63; 2026-03-01: 2.63; 2026-04-01: 2.63
3L Total | 3L Total | Diluted_Stoping_Tonnes | 2024-10-01: 4045; 2024-11-01: 4553; 2024-12-01: 7991; 2025-01-01: 7337; 2025-02-01: 5803; 2025-03-01: 4139; 2025-04-01: 1872; 2025-05-01: 119; 2025-06-01: 168; 2025-07-01: 2280; 2025-08-01: 4196; 2025-09-01: 6299; 2025-10-01: 6067; 2025-11-01: 5617; 2025-12-01: 5393; 2026-01-01: 4904; 2026-02-01: 1423
3L Total | 3L Total | Au_dil | 2024-10-01: 3.11; 2024-11-01: 3.03; 2024-12-01: 2.43; 2025-01-01: 1.91; 2025-02-01: 1.85; 2025-03-01: 2.19; 2025-04-01: 1.72; 2025-05-01: 1.72; 2025-06-01: 1.58; 2025-07-01: 1.65; 2025-08-01: 2.15; 2025-09-01: 2.51; 2025-10-01: 2.58; 2025-11-01: 2.58; 2025-12-01: 2.58; 2026-01-01: 2.59; 2026-02-01: 2.63
4L | 4L_W10B_STP | Diluted_Stoping_Tonnes | 2024-06-01: 2809; 2024-07-01: 3033; 2024-08-01: 2914
4L | 4L_W10B_STP | Au_dil | 2024-06-01: 2.35; 2024-07-01: 2.35; 2024-08-01: 2.35
4L | 4L_W11A_STP | Diluted_Stoping_Tonnes | 2024-09-01: 2809; 2024-10-01: 1149
4L | 4L_W11A_STP | Au_dil | 2024-09-01: 1.09; 2024-10-01: 1.09
4L | 4L_W11B_STP | Diluted_Stoping_Tonnes | 2024-10-01: 1256; 2024-11-01: 1628
4L | 4L_W11B_STP | Au_dil | 2024-10-01: 0.78; 2024-11-01: 0.78
4L | 4L_W13B_STP | Diluted_Stoping_Tonnes | 2024-06-01: 1873; 2024-07-01: 122
4L | 4L_W13B_STP | Au_dil | 2024-06-01: 0.3; 2024-07-01: 0.3
4L | 4L_W14A_STP | Diluted_Stoping_Tonnes | 2024-07-01: 3033; 2024-08-01: 25
4L | 4L_W14A_STP | Au_dil | 2024-07-01: 0.96; 2024-08-01: 0.96
4L | 4L_W14B_STP | Diluted_Stoping_Tonnes | 2024-07-01: 1331; 2024-08-01: 1947; 2024-09-01: 877
4L | 4L_W14B_STP | Au_dil | 2024-07-01: 2.88; 2024-08-01: 2.88; 2024-09-01: 2.88
4L | 4L_W15A_STP | Diluted_Stoping_Tonnes | 2024-06-01: 1872; 2024-07-01: 2022; 2024-08-01: 1282
4L | 4L_W15A_STP | Au_dil | 2024-06-01: 1.21; 2024-07-01: 1.21; 2024-08-01: 1.21
4L | 4L_W15B_STP | Diluted_Stoping_Tonnes | 2024-10-01: 1685; 2024-11-01: 2921; 2024-12-01: 2696; 2025-01-01: 2921; 2025-02-01: 345
4L | 4L_W15B_STP | Au_dil | 2024-10-01: 2.71; 2024-11-01: 2.71; 2024-12-01: 2.71; 2025-01-01: 2.71; 2025-02-01: 2.71
4L | 4L_W15C_STP | Diluted_Stoping_Tonnes | 2024-09-01: 995; 2024-10-01: 2022; 2024-11-01: 1947; 2024-12-01: 1798; 2025-01-01: 1947; 2025-02-01: 1723; 2025-03-01: 1798; 2025-04-01: 1873; 2025-05-01: 1947; 2025-06-01: 1873; 2025-07-01: 1534
4L | 4L_W15C_STP | Au_dil | 2024-09-01: 1.4; 2024-10-01: 1.4; 2024-11-01: 1.4; 2024-12-01: 1.4; 2025-01-01: 1.4; 2025-02-01: 1.4; 2025-03-01: 1.4; 2025-04-01: 1.4; 2025-05-01: 1.4; 2025-06-01: 1.4; 2025-07-01: 1.4
4L | 4L_W16A_STP | Diluted_Stoping_Tonnes | 2024-06-01: 1897
4L | 4L_W16A_STP | Au_dil | 2024-06-01: 1.22
4L | 4L_W16B_STP | Diluted_Stoping_Tonnes | 2024-06-01: 1872; 2024-07-01: 903; 2024-10-01: 1011; 2024-11-01: 974; 2024-12-01: 899; 2025-01-01: 408
4L | 4L_W16B_STP | Au_dil | 2024-06-01: 2.32; 2024-07-01: 2.32; 2024-10-01: 1.28; 2024-11-01: 1.28; 2024-12-01: 1.28; 2025-01-01: 1.28
4L | 4L_W16C_STP | Diluted_Stoping_Tonnes | 2024-10-01: 3033; 2024-11-01: 2921; 2024-12-01: 2609
4L | 4L_W16C_STP | Au_dil | 2024-10-01: 1.23; 2024-11-01: 1.23; 2024-12-01: 1.23
4L | 4L_W18A_STP | Diluted_Stoping_Tonnes
4L | 4L_W18A_STP | Au_dil
4L | 4L_W18B_STP | Diluted_Stoping_Tonnes
4L | 4L_W18B_STP | Au_dil
4L | 4L_W23_STP | Diluted_Stoping_Tonnes | 2025-01-01: 3033; 2025-02-01: 2921; 2025-03-01: 2534
4L | 4L_W23_STP | Au_dil | 2025-01-01: 1.81; 2025-02-01: 1.81; 2025-03-01: 1.81
4L Total | 4L Total | Diluted_Stoping_Tonnes | 2024-06-01: 10324; 2024-07-01: 10446; 2024-08-01: 6167; 2024-09-01: 4681; 2024-10-01: 23269; 2024-11-01: 13312; 2024-12-01: 11435; 2025-01-01: 6690; 2025-02-01: 3790; 2025-03-01: 3218; 2025-04-01: 1873; 2025-05-01: 1947; 2025-06-01: 1873; 2025-07-01: 1534
4L Total | 4L Total | Au_dil | 2024-06-01: 1.56; 2024-07-01: 1.77; 2024-08-01: 2.27; 2024-09-01: 1.49; 2024-10-01: 1.59; 2024-11-01: 1.66; 2024-12-01: 1.75; 2025-01-01: 1.96; 2025-02-01: 1.75; 2025-03-01: 1.63; 2025-04-01: 1.4; 2025-05-01: 1.4; 2025-06-01: 1.4; 2025-07-01: 1.4
5L | 5L_W10B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 85; 2025-04-01: 1872; 2025-05-01: 1947; 2025-06-01: 110
5L | 5L_W10B_STP | Au_dil | 2025-03-01: 3.33; 2025-04-01: 3.33; 2025-05-01: 3.33; 2025-06-01: 3.33
5L | 5L_W11A_STP | Diluted_Stoping_Tonnes | 2025-03-01: 85; 2025-04-01: 1873; 2025-05-01: 512
5L | 5L_W11A_STP | Au_dil | 2025-03-01: 2.94; 2025-04-01: 2.94; 2025-05-01: 2.94
5L | 5L_W11B_STP | Diluted_Stoping_Tonnes | 2025-05-01: 1435; 2025-06-01: 1210
5L | 5L_W11B_STP | Au_dil | 2025-05-01: 1.89; 2025-06-01: 1.89
5L | 5L_W16A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 93; 2025-11-01: 1872; 2025-12-01: 1798; 2026-01-01: 1427
5L | 5L_W16A_STP | Au_dil | 2025-10-01: 1.6; 2025-11-01: 1.6; 2025-12-01: 1.6; 2026-01-01: 1.6
5L | 5L_W16B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1798; 2026-06-01: 1232
5L | 5L_W16B_STP | Au_dil | 2026-04-01: 1.4; 2026-05-01: 1.4; 2026-06-01: 1.4
5L | 5L_W18A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1872; 2026-05-01: 1798; 2026-06-01: 1504
5L | 5L_W18A_STP | Au_dil | 2026-04-01: 3.28; 2026-05-01: 3.28; 2026-06-01: 3.28
5L | 5L_W18B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1798; 2026-06-01: 1388
5L | 5L_W18B_STP | Au_dil | 2026-04-01: 2.8; 2026-05-01: 2.8; 2026-06-01: 2.8
5L | 5L_W25A_STP | Diluted_Stoping_Tonnes | 2025-07-01: 1610; 2025-08-01: 1798; 2025-09-01: 1469
5L | 5L_W25A_STP | Au_dil | 2025-07-01: 3.23; 2025-08-01: 3.23; 2025-09-01: 3.23
5L | 5L_W25B_STP | Diluted_Stoping_Tonnes | 2025-08-01: 1036; 2025-09-01: 1947; 2025-10-01: 2022; 2025-11-01: 1416
5L | 5L_W25B_STP | Au_dil | 2025-08-01: 3.97; 2025-09-01: 3.97; 2025-10-01: 3.97; 2025-11-01: 3.97
5L | 5L_W5A_STP | Diluted_Stoping_Tonnes | 2024-12-01: 1685; 2025-01-01: 351
5L | 5L_W5A_STP | Au_dil | 2024-12-01: 1.82; 2025-01-01: 1.82
5L | 5L_W5B_STP | Diluted_Stoping_Tonnes | 2024-11-01: 1947; 2024-12-01: 113
5L | 5L_W5B_STP | Au_dil | 2024-11-01: 1.7; 2024-12-01: 1.7
5L | 5L_W6A_STP | Diluted_Stoping_Tonnes | 2025-02-01: 1723; 2025-03-01: 184
5L | 5L_W6A_STP | Au_dil | 2025-02-01: 0.82; 2025-03-01: 0.82
5L | 5L_W6B_STP | Diluted_Stoping_Tonnes | 2025-01-01: 1908
5L | 5L_W6B_STP | Au_dil | 2025-01-01: 0.92
5L | 5L_W7A_STP | Diluted_Stoping_Tonnes | 2025-01-01: 1947; 2025-02-01: 1010
5L | 5L_W7A_STP | Au_dil | 2025-01-01: 0.53; 2025-02-01: 0.53
5L | 5L_W7B_STP | Diluted_Stoping_Tonnes | 2025-03-01: 1792; 2025-04-01: 1147
5L | 5L_W7B_STP | Au_dil | 2025-03-01: 0.69; 2025-04-01: 0.69
5L | 5L_W8A_STP | Diluted_Stoping_Tonnes | 2025-02-01: 712; 2025-03-01: 1798; 2025-04-01: 1872; 2025-05-01: 371
5L | 5L_W8A_STP | Au_dil | 2025-02-01: 3.3; 2025-03-01: 3.3; 2025-04-01: 3.3; 2025-05-01: 3.3
5L | 5L_W8B_STP | Diluted_Stoping_Tonnes | 2025-04-01: 725; 2025-05-01: 1947; 2025-06-01: 1823
5L | 5L_W8B_STP | Au_dil | 2025-04-01: 3.97; 2025-05-01: 3.97; 2025-06-01: 3.97
5L Total | 5L Total | Diluted_Stoping_Tonnes | 2024-11-01: 1947; 2024-12-01: 1798; 2025-01-01: 4206; 2025-02-01: 3445; 2025-03-01: 3943; 2025-04-01: 7490; 2025-05-01: 6213; 2025-06-01: 3143; 2025-07-01: 1610; 2025-08-01: 2834; 2025-09-01: 3417; 2025-10-01: 2115; 2025-11-01: 3289; 2025-12-01: 1798; 2026-01-01: 1427; 2026-04-01: 5618; 2026-05-01: 5393; 2026-06-01: 4124
5L Total | 5L Total | Au_dil | 2024-11-01: 1.7; 2024-12-01: 1.81; 2025-01-01: 0.82; 2025-02-01: 1.25; 2025-03-01: 1.99; 2025-04-01: 2.88; 2025-05-01: 3.17; 2025-06-01: 3.15; 2025-07-01: 3.23; 2025-08-01: 3.5; 2025-09-01: 3.65; 2025-10-01: 3.87; 2025-11-01: 2.62; 2025-12-01: 1.6; 2026-01-01: 1.6; 2026-04-01: 2.49; 2026-05-01: 2.49; 2026-06-01: 2.56
6L | 6L_E1_STP | Diluted_Stoping_Tonnes | 2024-12-01: 1348; 2025-01-01: 2921; 2025-02-01: 2584; 2025-03-01: 2696; 2025-04-01: 2809; 2025-05-01: 2921; 2025-06-01: 2809; 2025-07-01: 3033; 2025-08-01: 2696; 2025-09-01: 2921; 2025-10-01: 3033; 2025-11-01: 2809; 2025-12-01: 2696; 2026-01-01: 2921; 2026-02-01: 2584; 2026-03-01: 1844
6L | 6L_E1_STP | Au_dil | 2024-12-01: 2.83; 2025-01-01: 2.83; 2025-02-01: 2.83; 2025-03-01: 2.83; 2025-04-01: 2.83; 2025-05-01: 2.83; 2025-06-01: 2.83; 2025-07-01: 2.83; 2025-08-01: 2.83; 2025-09-01: 2.83; 2025-10-01: 2.83; 2025-11-01: 2.83; 2025-12-01: 2.83; 2026-01-01: 2.83; 2026-02-01: 2.83; 2026-03-01: 2.83
6L | 6L_W13_STP | Diluted_Stoping_Tonnes | 2025-01-01: 1947; 2025-02-01: 207
6L | 6L_W13_STP | Au_dil | 2025-01-01: 3.63; 2025-02-01: 3.63
6L | 6L_W14A_STP | Diluted_Stoping_Tonnes | 2024-12-01: 1798; 2025-01-01: 1947; 2025-02-01: 481
6L | 6L_W14A_STP | Au_dil | 2024-12-01: 2.87; 2025-01-01: 2.87; 2025-02-01: 2.87
6L | 6L_W14B_STP | Diluted_Stoping_Tonnes | 2025-02-01: 1242; 2025-03-01: 1798; 2025-04-01: 1282
6L | 6L_W14B_STP | Au_dil | 2025-02-01: 2.45; 2025-03-01: 2.45; 2025-04-01: 2.45
6L | 6L_W19A_STP | Diluted_Stoping_Tonnes | 2025-05-01: 1202; 2025-06-01: 1873; 2025-07-01: 1680
6L | 6L_W19A_STP | Au_dil | 2025-05-01: 2.84; 2025-06-01: 2.84; 2025-07-01: 2.84
6L | 6L_W19B_STP | Diluted_Stoping_Tonnes | 2025-06-01: 1813; 2025-07-01: 2022; 2025-08-01: 1798; 2025-09-01: 233
6L | 6L_W19B_STP | Au_dil | 2025-06-01: 3.2; 2025-07-01: 3.2; 2025-08-01: 3.2; 2025-09-01: 3.2
6L | 6L_W2_STP | Diluted_Stoping_Tonnes | 2025-03-01: 970; 2025-04-01: 2809; 2025-05-01: 2921; 2025-06-01: 2809; 2025-07-01: 3033; 2025-08-01: 2696; 2025-09-01: 2921; 2025-10-01: 3033; 2025-11-01: 2809; 2025-12-01: 2696; 2026-01-01: 2345
6L | 6L_W2_STP | Au_dil | 2025-03-01: 2.31; 2025-04-01: 2.31; 2025-05-01: 2.31; 2025-06-01: 2.31; 2025-07-01: 2.31; 2025-08-01: 2.31; 2025-09-01: 2.31; 2025-10-01: 2.31; 2025-11-01: 2.31; 2025-12-01: 2.31; 2026-01-01: 2.31
6L | 6L_W27_STP | Diluted_Stoping_Tonnes | 2025-05-01: 18; 2025-06-01: 1148
6L | 6L_W27_STP | Au_dil | 2025-05-01: 3.97; 2025-06-01: 3.97
6L | 6L_W28_STP | Diluted_Stoping_Tonnes | 2025-04-01: 635
6L | 6L_W28_STP | Au_dil | 2025-04-01: 2.85
6L | 6L_W4_STP | Diluted_Stoping_Tonnes | 2025-03-01: 945; 2025-04-01: 1873; 2025-05-01: 1947; 2025-06-01: 1873; 2025-07-01: 2022; 2025-08-01: 1481
6L | 6L_W4_STP | Au_dil | 2025-03-01: 2.41; 2025-04-01: 2.41; 2025-05-01: 2.41; 2025-06-01: 2.41; 2025-07-01: 2.41; 2025-08-01: 2.41
6L | 6L_W6_STP | Diluted_Stoping_Tonnes | 2024-12-01: 899; 2025-01-01: 1947; 2025-02-01: 1723; 2025-03-01: 1710
6L | 6L_W6_STP | Au_dil | 2024-12-01: 3.06; 2025-01-01: 3.06; 2025-02-01: 1.34; 2025-03-01: 1.5452
6L | 6L_W8_STP | Diluted_Stoping_Tonnes | 2024-12-01: 899; 2025-01-01: 1807
6L | 6L_W8_STP | Au_dil | 2024-12-01: 1.57; 2025-01-01: 1.57
6L | 6L_W9_STP | Diluted_Stoping_Tonnes | 2024-12-01: 899; 2025-01-01: 1947; 2025-02-01: 1723; 2025-03-01: 121
6L | 6L_W9_STP | Au_dil | 2024-12-01: 2.7; 2025-01-01: 2.7; 2025-02-01: 2.7; 2025-03-01: 2.7
6L Total | 6L Total | Diluted_Stoping_Tonnes | 2024-12-01: 5842; 2025-01-01: 12518; 2025-02-01: 8163; 2025-03-01: 8037; 2025-04-01: 9407; 2025-05-01: 9010; 2025-06-01: 12324; 2025-07-01: 11792; 2025-08-01: 8671; 2025-09-01: 6075; 2025-10-01: 6067; 2025-11-01: 5618; 2025-12-01: 5393; 2026-01-01: 5266; 2026-02-01: 2584; 2026-03-01: 1844
6L Total | 6L Total | Au_dil | 2024-12-01: 2.66; 2025-01-01: 2.79; 2025-02-01: 2.46; 2025-03-01: 2.35; 2025-04-01: 2.54; 2025-05-01: 2.57; 2025-06-01: 2.81; 2025-07-01: 2.69; 2025-08-01: 2.67; 2025-09-01: 2.59; 2025-10-01: 2.57; 2025-11-01: 2.57; 2025-12-01: 2.57; 2026-01-01: 2.6; 2026-02-01: 2.83; 2026-03-01: 2.83
6L_A | 6L_A_E4_STP | Diluted_Stoping_Tonnes | 2026-01-01: 14; 2026-02-01: 0; 2026-03-01: 1798; 2026-04-01: 1020
6L_A | 6L_A_E4_STP | Au_dil | 2026-01-01: 1.94; 2026-03-01: 1.94; 2026-04-01: 1.94
6L_A | 6L_A_E5_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1399
6L_A | 6L_A_E5_STP | Au_dil | 2026-04-01: 3.22; 2026-05-01: 3.22
6L_A | 6L_A_W11_STP | Diluted_Stoping_Tonnes | 2025-06-01: 625; 2025-07-01: 269
6L_A | 6L_A_W11_STP | Au_dil | 2025-06-01: 3.05; 2025-07-01: 3.05
6L_A | 6L_A_W12_STP | Diluted_Stoping_Tonnes | 2025-03-01: 1036; 2025-04-01: 1007
6L_A | 6L_A_W12_STP | Au_dil | 2025-03-01: 2.01; 2025-04-01: 2.01
6L_A | 6L_A_W14_STP | Diluted_Stoping_Tonnes | 2025-05-01: 1211; 2025-06-01: 959
6L_A | 6L_A_W14_STP | Au_dil | 2025-05-01: 1.64; 2025-06-01: 1.64
6L_A | 6L_A_W19_STP | Diluted_Stoping_Tonnes | 2025-06-01: 913; 2025-07-01: 2022; 2025-08-01: 176
6L_A | 6L_A_W19_STP | Au_dil | 2025-06-01: 3.97; 2025-07-01: 3.97; 2025-08-01: 3.97
6L_A | 6L_A_W2_STP | Diluted_Stoping_Tonnes | 2025-10-01: 2933; 2025-11-01: 2809; 2025-12-01: 2696; 2026-01-01: 2921; 2026-02-01: 2584; 2026-03-01: 1980
6L_A | 6L_A_W2_STP | Au_dil | 2025-10-01: 2.17; 2025-11-01: 2.17; 2025-12-01: 2.17; 2026-01-01: 2.17; 2026-02-01: 2.17; 2026-03-01: 2.17
6L_A | 6L_A_W26_STP | Diluted_Stoping_Tonnes | 2025-07-01: 87; 2025-08-01: 899; 2025-09-01: 974; 2025-10-01: 2
6L_A | 6L_A_W26_STP | Au_dil | 2025-07-01: 1.55; 2025-08-01: 1.55; 2025-09-01: 1.55; 2025-10-01: 1.55
6L_A | 6L_A_W4_STP | Diluted_Stoping_Tonnes | 2025-07-01: 229; 2025-08-01: 899; 2025-09-01: 974; 2025-10-01: 509
6L_A | 6L_A_W4_STP | Au_dil | 2025-07-01: 3.49; 2025-08-01: 3.49; 2025-09-01: 3.49; 2025-10-01: 3.49
6L_A | 6L_A_W6_STP | Diluted_Stoping_Tonnes | 2025-07-01: 877; 2025-08-01: 899; 2025-09-01: 509
6L_A | 6L_A_W6_STP | Au_dil | 2025-07-01: 1.03; 2025-08-01: 1.03; 2025-09-01: 1.03
6L_A | 6L_A_W8_STP | Diluted_Stoping_Tonnes | 2025-08-01: 1621; 2025-09-01: 1947; 2025-10-01: 2022; 2025-11-01: 1872; 2025-12-01: 1798; 2026-01-01: 786
6L_A | 6L_A_W8_STP | Au_dil | 2025-08-01: 2.45; 2025-09-01: 2.45; 2025-10-01: 2.45; 2025-11-01: 2.45; 2025-12-01: 2.45; 2026-01-01: 2.45
6L_A Total | 6L_A Total | Diluted_Stoping_Tonnes | 2025-03-01: 1036; 2025-04-01: 1007; 2025-05-01: 1211; 2025-06-01: 2498; 2025-07-01: 3484; 2025-08-01: 4494; 2025-09-01: 4404; 2025-10-01: 5466; 2025-11-01: 4681; 2025-12-01: 4494; 2026-01-01: 3721; 2026-02-01: 2584; 2026-03-01: 3778; 2026-04-01: 2892; 2026-05-01: 1399
6L_A Total | 6L_A Total | Au_dil | 2025-03-01: 2.01; 2025-04-01: 2.01; 2025-05-01: 1.64; 2025-06-01: 2.85; 2025-07-01: 3.07; 2025-08-01: 2.25; 2025-09-01: 2.31; 2025-10-01: 2.39; 2025-11-01: 2.28; 2025-12-01: 2.28; 2026-01-01: 2.23; 2026-02-01: 2.17; 2026-03-01: 2.06; 2026-04-01: 2.77; 2026-05-01: 3.22
7L | 7L_W10A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 1723; 2026-03-01: 1450
7L | 7L_W10A_STP | Au_dil | 2026-02-01: 1.34; 2026-03-01: 1.34
7L | 7L_W10B_STP | Diluted_Stoping_Tonnes | 2026-01-01: 434; 2026-02-01: 1723; 2026-03-01: 1665
7L | 7L_W10B_STP | Au_dil | 2026-01-01: 3.12; 2026-02-01: 3.12; 2026-03-01: 3.12
7L | 7L_W14A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 1947; 2026-02-01: 1723; 2026-03-01: 238
7L | 7L_W14A_STP | Au_dil | 2026-01-01: 1.91; 2026-02-01: 1.91; 2026-03-01: 1.91
7L | 7L_W14B_STP | Diluted_Stoping_Tonnes | 2025-11-01: 594; 2025-12-01: 1798; 2026-01-01: 1213
7L | 7L_W14B_STP | Au_dil | 2025-11-01: 2.88; 2025-12-01: 2.88; 2026-01-01: 2.88
7L | 7L_W18A_STP | Diluted_Stoping_Tonnes | 2025-09-01: 128; 2025-10-01: 2022; 2025-11-01: 1872; 2025-12-01: 1098
7L | 7L_W18A_STP | Au_dil | 2025-09-01: 3.61; 2025-10-01: 3.61; 2025-11-01: 3.61; 2025-12-01: 3.61
7L | 7L_W18B_STP | Diluted_Stoping_Tonnes | 2025-10-01: 1611; 2025-11-01: 1873; 2025-12-01: 1798; 2026-01-01: 24
7L | 7L_W18B_STP | Au_dil | 2025-10-01: 2.87; 2025-11-01: 2.87; 2025-12-01: 2.87; 2026-01-01: 2.87
7L | 7L_W1B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 2921; 2025-10-01: 3033; 2025-11-01: 2809; 2025-12-01: 2696; 2026-01-01: 2921; 2026-02-01: 2584; 2026-03-01: 2696; 2026-04-01: 874
7L | 7L_W1B_STP | Au_dil | 2025-09-01: 2.43; 2025-10-01: 2.43; 2025-11-01: 2.43; 2025-12-01: 2.43; 2026-01-01: 2.43; 2026-02-01: 2.43; 2026-03-01: 2.43; 2026-04-01: 2.43
7L | 7L_W20A_STP | Diluted_Stoping_Tonnes | 2026-03-01: 1798; 2026-04-01: 186
7L | 7L_W20A_STP | Au_dil | 2026-03-01: 3.97; 2026-04-01: 3.97
7L | 7L_W20B_STP | Diluted_Stoping_Tonnes | 2026-01-01: 40; 2026-02-01: 0; 2026-03-01: 1798; 2026-04-01: 841
7L | 7L_W20B_STP | Au_dil | 2026-01-01: 3.97; 2026-03-01: 3.97; 2026-04-01: 3.97
7L | 7L_W22A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1798; 2026-06-01: 593
7L | 7L_W22A_STP | Au_dil | 2026-04-01: 2.53; 2026-05-01: 2.53; 2026-06-01: 2.53
7L | 7L_W22B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1798; 2026-06-01: 588
7L | 7L_W22B_STP | Au_dil | 2026-04-01: 3.5; 2026-05-01: 3.5; 2026-06-01: 3.5
7L | 7L_W6_STP | Diluted_Stoping_Tonnes | 2025-10-01: 2946; 2025-11-01: 2809; 2025-12-01: 4494; 2026-01-01: 1853; 2026-03-01: 3595; 2026-04-01: 2635; 2026-05-01: 1798; 2026-06-01: 1356
7L | 7L_W6_STP | Au_dil | 2025-10-01: 2.55; 2025-11-01: 2.55; 2025-12-01: 2.18; 2026-01-01: 2.5; 2026-03-01: 1.93; 2026-04-01: 1.85; 2026-05-01: 1.75; 2026-06-01: 1.75
7L Total | 7L Total | Diluted_Stoping_Tonnes | 2025-09-01: 3049; 2025-10-01: 9612; 2025-11-01: 9956; 2025-12-01: 11884; 2026-01-01: 8433; 2026-02-01: 7752; 2026-03-01: 13240; 2026-04-01: 8281; 2026-05-01: 5393; 2026-06-01: 2537
7L Total | 7L Total | Au_dil | 2025-09-01: 2.48; 2025-10-01: 2.79; 2025-11-01: 2.8; 2025-12-01: 2.58; 2026-01-01: 2.43; 2026-02-01: 2.23; 2026-03-01: 2.67; 2026-04-01: 2.7; 2026-05-01: 2.59; 2026-06-01: 2.34
8L | 8L_E5A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 2921; 2026-02-01: 2562
8L | 8L_E5A_STP | Au_dil | 2026-01-01: 2.24; 2026-02-01: 2.24
8L | 8L_E5B_STP | Diluted_Stoping_Tonnes | 2025-09-01: 1947; 2025-10-01: 2022; 2025-11-01: 876
8L | 8L_E5B_STP | Au_dil | 2025-09-01: 2.64; 2025-10-01: 2.64; 2025-11-01: 2.64
8L | 8L_W10A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 1723; 2026-03-01: 1580
8L | 8L_W10A_STP | Au_dil | 2026-02-01: 3.97; 2026-03-01: 3.97
8L | 8L_W10B_STP | Diluted_Stoping_Tonnes | 2026-01-01: 1947; 2026-02-01: 1623
8L | 8L_W10B_STP | Au_dil | 2026-01-01: 2.55; 2026-02-01: 2.55
8L | 8L_W14A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 1723; 2026-03-01: 1798; 2026-04-01: 439
8L | 8L_W14A_STP | Au_dil | 2026-02-01: 3.97; 2026-03-01: 3.97; 2026-04-01: 3.97
8L | 8L_W14B_STP | Diluted_Stoping_Tonnes | 2025-12-01: 1002; 2026-01-01: 1947; 2026-02-01: 1318
8L | 8L_W14B_STP | Au_dil | 2025-12-01: 2.23; 2026-01-01: 2.23; 2026-02-01: 2.23
8L | 8L_W16A_STP | Diluted_Stoping_Tonnes | 2026-01-01: 1947; 2026-02-01: 1255
8L | 8L_W16A_STP | Au_dil | 2026-01-01: 2.94; 2026-02-01: 2.94
8L | 8L_W16B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 724; 2026-03-01: 1798; 2026-04-01: 800
8L | 8L_W16B_STP | Au_dil | 2026-02-01: 2.36; 2026-03-01: 2.36; 2026-04-01: 2.36
8L | 8L_W18A_STP | Diluted_Stoping_Tonnes | 2026-02-01: 1723; 2026-03-01: 1798; 2026-04-01: 633
8L | 8L_W18A_STP | Au_dil | 2026-02-01: 3.08; 2026-03-01: 3.08; 2026-04-01: 3.08
8L | 8L_W18B_STP | Diluted_Stoping_Tonnes | 2026-02-01: 1723; 2026-03-01: 1798; 2026-04-01: 927
8L | 8L_W18B_STP | Au_dil | 2026-02-01: 3.6; 2026-03-01: 3.6; 2026-04-01: 3.6
8L | 8L_W20A_STP | Diluted_Stoping_Tonnes | 2025-10-01: 1158; 2025-11-01: 398
8L | 8L_W20A_STP | Au_dil | 2025-10-01: 2.85; 2025-11-01: 2.85
8L | 8L_W20B_STP | Diluted_Stoping_Tonnes | 2025-10-01: 831; 2025-11-01: 776
8L | 8L_W20B_STP | Au_dil | 2025-10-01: 2.73; 2025-11-01: 2.73
8L | 8L_W22A_STP | Diluted_Stoping_Tonnes | 2026-03-01: 1798; 2026-04-01: 1872; 2026-05-01: 940
8L | 8L_W22A_STP | Au_dil | 2026-03-01: 2.73; 2026-04-01: 2.73; 2026-05-01: 2.73
8L | 8L_W22B_STP | Diluted_Stoping_Tonnes | 2026-03-01: 533; 2026-04-01: 1872; 2026-05-01: 1798; 2026-06-01: 872
8L | 8L_W22B_STP | Au_dil | 2026-03-01: 2.74; 2026-04-01: 2.74; 2026-05-01: 2.74; 2026-06-01: 2.74
8L | 8L_W24A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 1798; 2026-06-01: 949
8L | 8L_W24A_STP | Au_dil | 2026-04-01: 3.75; 2026-05-01: 3.75; 2026-06-01: 3.75
8L | 8L_W24B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1872; 2026-05-01: 1798; 2026-06-01: 1947; 2026-07-01: 196
8L | 8L_W24B_STP | Au_dil | 2026-04-01: 3.66; 2026-05-01: 3.66; 2026-06-01: 3.66; 2026-07-01: 3.66
8L | 8L_W7A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 842
8L | 8L_W7A_STP | Au_dil | 2026-04-01: 3.44
8L | 8L_W7B_STP | Diluted_Stoping_Tonnes | 2026-04-01: 602
8L | 8L_W7B_STP | Au_dil | 2026-04-01: 2.88
8L Total | 8L Total | Diluted_Stoping_Tonnes | 2025-09-01: 1947; 2025-10-01: 4011; 2025-11-01: 2050; 2025-12-01: 1002; 2026-01-01: 8763; 2026-02-01: 14371; 2026-03-01: 11102; 2026-04-01: 11734; 2026-05-01: 6333; 2026-06-01: 3769; 2026-07-01: 196
8L Total | 8L Total | Au_dil | 2025-09-01: 2.64; 2025-10-01: 2.72; 2025-11-01: 2.71; 2025-12-01: 2.23; 2026-01-01: 2.46; 2026-02-01: 3.02; 2026-03-01: 3.25; 2026-04-01: 3.21; 2026-05-01: 3.29; 2026-06-01: 3.47; 2026-07-01: 3.66
9L | 9L_E5_STP | Diluted_Stoping_Tonnes | 2026-05-01: 2696; 2026-06-01: 2921; 2026-07-01: 368
9L | 9L_E5_STP | Au_dil | 2026-05-01: 1.99; 2026-06-01: 1.99; 2026-07-01: 1.99
9L | 9L_E9_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1798; 2026-06-01: 696
9L | 9L_E9_STP | Au_dil | 2026-05-01: 2.29; 2026-06-01: 2.29
9L | 9L_W1_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1873; 2026-12-01: 1798; 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1873; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1873; 2028-01-01: 1708
9L | 9L_W1_STP | Au_dil | 2026-07-01: 1.8; 2026-08-01: 1.8; 2026-09-01: 1.8; 2026-10-01: 1.8; 2026-11-01: 1.8; 2026-12-01: 1.8; 2027-01-01: 1.8; 2027-02-01: 1.8; 2027-03-01: 1.8; 2027-04-01: 1.8; 2027-05-01: 1.8; 2027-06-01: 1.8; 2027-07-01: 1.8; 2027-08-01: 1.8; 2027-09-01: 1.8; 2027-10-01: 1.8; 2027-11-01: 1.8; 2027-12-01: 1.8; 2028-01-01: 1.8
9L | 9L_W16A_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1798; 2026-06-01: 1020
9L | 9L_W16A_STP | Au_dil | 2026-05-01: 2.46; 2026-06-01: 2.46
9L | 9L_W16B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 1075
9L | 9L_W16B_STP | Au_dil | 2026-06-01: 2.68; 2026-07-01: 2.68
9L | 9L_W18A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 1323
9L | 9L_W18A_STP | Au_dil | 2026-06-01: 3.97; 2026-07-01: 3.97
9L | 9L_W18B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 1715
9L | 9L_W18B_STP | Au_dil | 2026-06-01: 3.97; 2026-07-01: 3.97
9L | 9L_W20A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 698; 2026-07-01: 1705
9L | 9L_W20A_STP | Au_dil | 2026-06-01: 3.53; 2026-07-01: 3.53
9L | 9L_W20B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 1964
9L | 9L_W20B_STP | Au_dil | 2026-07-01: 3.2
9L | 9L_W22A_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 1602
9L | 9L_W22A_STP | Au_dil | 2026-07-01: 3.01; 2026-08-01: 3.01
9L | 9L_W22B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 1798; 2026-09-01: 273
9L | 9L_W22B_STP | Au_dil | 2026-07-01: 2.45; 2026-08-01: 2.45; 2026-09-01: 2.45
9L | 9L_W24_STP | Diluted_Stoping_Tonnes | 2026-07-01: 1126
9L | 9L_W24_STP | Au_dil | 2026-07-01: 1.97
9L | 9L_W4_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 747
9L | 9L_W4_STP | Au_dil | 2026-07-01: 1.92; 2026-08-01: 1.92; 2026-09-01: 1.92; 2026-10-01: 1.92; 2026-11-01: 1.92; 2026-12-01: 1.92; 2027-01-01: 1.92; 2027-02-01: 1.92; 2027-03-01: 1.92; 2027-04-01: 1.92
9L | 9L_W6A_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 933
9L | 9L_W6A_STP | Au_dil | 2026-07-01: 3.97; 2026-08-01: 3.97
9L | 9L_W6B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 1886
9L | 9L_W6B_STP | Au_dil | 2026-07-01: 3.79
9L Total | 9L Total | Diluted_Stoping_Tonnes | 2026-05-01: 6292; 2026-06-01: 11178; 2026-07-01: 21273; 2026-08-01: 7927; 2026-09-01: 4167; 2026-10-01: 4045; 2026-11-01: 3745; 2026-12-01: 3595; 2027-01-01: 3745; 2027-02-01: 3595; 2027-03-01: 3595; 2027-04-01: 2619; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1873; 2028-01-01: 1708
9L Total | 9L Total | Au_dil | 2026-05-01: 2.21; 2026-06-01: 2.96; 2026-07-01: 3.01; 2026-08-01: 2.47; 2026-09-01: 1.9; 2026-10-01: 1.86; 2026-11-01: 1.86; 2026-12-01: 1.86; 2027-01-01: 1.86; 2027-02-01: 1.86; 2027-03-01: 1.86; 2027-04-01: 1.83; 2027-05-01: 1.8; 2027-06-01: 1.8; 2027-07-01: 1.8; 2027-08-01: 1.8; 2027-09-01: 1.8; 2027-10-01: 1.8; 2027-11-01: 1.8; 2027-12-01: 1.8; 2028-01-01: 1.8
10L | 10L_E1A_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 2022; 2026-08-01: 188
10L | 10L_E1A_STP | Au_dil | 2026-06-01: 3; 2026-07-01: 3; 2026-08-01: 3
10L | 10L_E1B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 666
10L | 10L_E1B_STP | Au_dil | 2026-06-01: 2.95; 2026-07-01: 2.95
10L | 10L_E7A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 172
10L | 10L_E7A_STP | Au_dil | 2026-08-01: 3.97; 2026-09-01: 3.97; 2026-10-01: 3.97
10L | 10L_E7B_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1947; 2026-10-01: 1548
10L | 10L_E7B_STP | Au_dil | 2026-09-01: 3.97; 2026-10-01: 3.97
10L | 10L_E9_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1470
10L | 10L_E9_STP | Au_dil | 2026-09-01: 3.97
10L | 10L_W16A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 1873; 2026-05-01: 659
10L | 10L_W16A_STP | Au_dil | 2026-04-01: 3.21; 2026-05-01: 3.21
10L | 10L_W16B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 414
10L | 10L_W16B_STP | Au_dil | 2026-06-01: 3.67; 2026-07-01: 3.67
10L | 10L_W18A_STP | Diluted_Stoping_Tonnes | 2026-04-01: 815; 2026-05-01: 1673
10L | 10L_W18A_STP | Au_dil | 2026-04-01: 3.97; 2026-05-01: 3.97
10L | 10L_W18B_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1798; 2026-06-01: 718
10L | 10L_W18B_STP | Au_dil | 2026-05-01: 3.97; 2026-06-01: 3.97
10L | 10L_W1A_STP | Diluted_Stoping_Tonnes | 2026-05-01: 1024; 2026-06-01: 1947; 2026-07-01: 2022; 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1872; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 191
10L | 10L_W1A_STP | Au_dil | 2026-05-01: 2.26; 2026-06-01: 2.26; 2026-07-01: 2.26; 2026-08-01: 2.26; 2026-09-01: 2.26; 2026-10-01: 2.26; 2026-11-01: 2.26; 2026-12-01: 2.26; 2027-01-01: 2.26; 2027-02-01: 2.26; 2027-03-01: 2.26; 2027-04-01: 2.26; 2027-05-01: 2.26; 2027-06-01: 2.26; 2027-07-01: 2.26; 2027-08-01: 2.26; 2027-09-01: 2.26; 2027-10-01: 2.26
10L | 10L_W1B_STP | Diluted_Stoping_Tonnes | 2026-06-01: 1947; 2026-07-01: 2022; 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1873; 2026-12-01: 1798; 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1873; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 624
10L | 10L_W1B_STP | Au_dil | 2026-06-01: 2.12; 2026-07-01: 2.12; 2026-08-01: 2.12; 2026-09-01: 2.12; 2026-10-01: 2.12; 2026-11-01: 2.12; 2026-12-01: 2.12; 2027-01-01: 2.12; 2027-02-01: 2.12; 2027-03-01: 2.12; 2027-04-01: 2.12; 2027-05-01: 2.12; 2027-06-01: 2.12; 2027-07-01: 2.12; 2027-08-01: 2.12
10L | 10L_W20A_STP | Diluted_Stoping_Tonnes | 2026-07-01: 2022; 2026-08-01: 1149
10L | 10L_W20A_STP | Au_dil | 2026-07-01: 3.97; 2026-08-01: 3.97
10L | 10L_W20B_STP | Diluted_Stoping_Tonnes | 2026-07-01: 36; 2026-08-01: 1798; 2026-09-01: 886
10L | 10L_W20B_STP | Au_dil | 2026-07-01: 3.58; 2026-08-01: 3.58; 2026-09-01: 3.58
10L | 10L_W22A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1204
10L | 10L_W22A_STP | Au_dil | 2026-08-01: 1.79
10L | 10L_W22B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 309
10L | 10L_W22B_STP | Au_dil | 2026-08-01: 2.49; 2026-09-01: 2.49
10L | 10L_W4A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1873; 2026-12-01: 1798; 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 407
10L | 10L_W4A_STP | Au_dil | 2026-08-01: 2.02; 2026-09-01: 2.02; 2026-10-01: 2.02; 2026-11-01: 2.02; 2026-12-01: 2.02; 2027-01-01: 2.02; 2027-02-01: 2.02; 2027-03-01: 2.02; 2027-04-01: 2.02
10L | 10L_W4B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 620; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1527
10L | 10L_W4B_STP | Au_dil | 2026-08-01: 2.12; 2026-09-01: 2.12; 2026-10-01: 2.12; 2026-11-01: 2.12; 2026-12-01: 2.12; 2027-01-01: 2.12; 2027-02-01: 2.12; 2027-03-01: 2.12
10L | 10L_W6A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 200
10L | 10L_W6A_STP | Au_dil | 2026-08-01: 3.97; 2026-09-01: 3.97; 2026-10-01: 3.97; 2026-11-01: 3.97
10L | 10L_W6B_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 275
10L | 10L_W6B_STP | Au_dil | 2026-09-01: 3.97; 2026-10-01: 3.97; 2026-11-01: 3.97
10L | 10L_W8A_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 1336
10L | 10L_W8A_STP | Au_dil | 2026-08-01: 3.05; 2026-09-01: 3.05; 2026-10-01: 3.05
10L | 10L_W8B_STP | Diluted_Stoping_Tonnes | 2026-08-01: 1798; 2026-09-01: 1947; 2026-10-01: 1628
10L | 10L_W8B_STP | Au_dil | 2026-08-01: 3.97; 2026-09-01: 3.97; 2026-10-01: 3.97
10L Total | 10L Total | Diluted_Stoping_Tonnes | 2026-04-01: 2688; 2026-05-01: 5154; 2026-06-01: 10455; 2026-07-01: 9206; 2026-08-01: 19339; 2026-09-01: 22139; 2026-10-01: 16817; 2026-11-01: 7966; 2026-12-01: 7190; 2027-01-01: 7490; 2027-02-01: 7190; 2027-03-01: 6920; 2027-04-01: 4152; 2027-05-01: 3595; 2027-06-01: 3895; 2027-07-01: 4045; 2027-08-01: 2421; 2027-09-01: 1947; 2027-10-01: 191
10L Total | 10L Total | Au_dil | 2026-04-01: 3.44; 2026-05-01: 3.54; 2026-06-01: 2.88; 2026-07-01: 2.89; 2026-08-01: 3; 2026-09-01: 3.21; 2026-10-01: 3.01; 2026-11-01: 2.24; 2026-12-01: 2.13; 2027-01-01: 2.13; 2027-02-01: 2.13; 2027-03-01: 2.13; 2027-04-01: 2.17; 2027-05-01: 2.19; 2027-06-01: 2.19; 2027-07-01: 2.19; 2027-08-01: 2.23; 2027-09-01: 2.26; 2027-10-01: 2.26
11L | 11L_E1A_STP | Diluted_Stoping_Tonnes | 2026-10-01: 1899; 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 355
11L | 11L_E1A_STP | Au_dil | 2026-10-01: 2.77; 2026-11-01: 2.77; 2026-12-01: 2.77; 2027-01-01: 2.77; 2027-02-01: 2.77; 2027-03-01: 2.77; 2027-04-01: 2.77
11L | 11L_E1B_STP | Diluted_Stoping_Tonnes | 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1873; 2027-05-01: 1798; 2027-06-01: 371
11L | 11L_E1B_STP | Au_dil | 2027-01-01: 3.19; 2027-02-01: 3.19; 2027-03-01: 3.19; 2027-04-01: 3.19; 2027-05-01: 3.19; 2027-06-01: 3.19
11L | 11L_E7A_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1798; 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 293
11L | 11L_E7A_STP | Au_dil | 2026-12-01: 1.14; 2027-01-01: 1.14; 2027-02-01: 1.14; 2027-03-01: 1.14
11L | 11L_E7B_STP | Diluted_Stoping_Tonnes | 2026-10-01: 1848; 2026-11-01: 1873; 2026-12-01: 1798; 2027-01-01: 1873; 2027-02-01: 1004
11L | 11L_E7B_STP | Au_dil | 2026-10-01: 2.46; 2026-11-01: 2.46; 2026-12-01: 2.46; 2027-01-01: 2.46; 2027-02-01: 2.46
11L | 11L_W10A_STP | Diluted_Stoping_Tonnes | 2027-01-01: 1872; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1872; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 128
11L | 11L_W10A_STP | Au_dil | 2027-01-01: 1.95; 2027-02-01: 1.95; 2027-03-01: 1.95; 2027-04-01: 1.95; 2027-05-01: 1.95; 2027-06-01: 1.95; 2027-07-01: 1.95
11L | 11L_W10B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 64; 2027-01-01: 1873; 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1873; 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1679
11L | 11L_W10B_STP | Au_dil | 2026-12-01: 1.94; 2027-01-01: 1.94; 2027-02-01: 1.94; 2027-03-01: 1.94; 2027-04-01: 1.94; 2027-05-01: 1.94; 2027-06-01: 1.94; 2027-07-01: 1.94; 2027-08-01: 1.94; 2027-09-01: 1.94
11L | 11L_W14A_STP | Diluted_Stoping_Tonnes | 2026-09-01: 933; 2026-10-01: 2022; 2026-11-01: 1873; 2026-12-01: 145
11L | 11L_W14A_STP | Au_dil | 2026-09-01: 1.83; 2026-10-01: 1.83; 2026-11-01: 1.83; 2026-12-01: 1.83
11L | 11L_W14B_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 473
11L | 11L_W14B_STP | Au_dil | 2026-11-01: 1.93; 2026-12-01: 1.93; 2027-01-01: 1.93
11L | 11L_W18A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1872; 2026-12-01: 1489
11L | 11L_W18A_STP | Au_dil | 2026-11-01: 3.76; 2026-12-01: 3.76
11L | 11L_W18B_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1873; 2026-12-01: 1798; 2027-01-01: 675
11L | 11L_W18B_STP | Au_dil | 2026-11-01: 3.21; 2026-12-01: 3.21; 2027-01-01: 3.21
11L | 11L_W4A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1553
11L | 11L_W4A_STP | Au_dil | 2026-11-01: 3.93; 2026-12-01: 3.93; 2027-01-01: 3.93; 2027-02-01: 3.93
11L | 11L_W4B_STP | Diluted_Stoping_Tonnes | 2026-11-01: 1872; 2026-12-01: 1798; 2027-01-01: 1872; 2027-02-01: 1760
11L | 11L_W4B_STP | Au_dil | 2026-11-01: 3.72; 2026-12-01: 3.72; 2027-01-01: 3.72; 2027-02-01: 3.72
11L | 11L_W6A_STP | Diluted_Stoping_Tonnes | 2026-11-01: 489; 2026-12-01: 1301
11L | 11L_W6A_STP | Au_dil | 2026-11-01: 2.4; 2026-12-01: 2.4
11L | 11L_W6B_STP | Diluted_Stoping_Tonnes | 2026-12-01: 1798; 2027-01-01: 721
11L | 11L_W6B_STP | Au_dil | 2026-12-01: 1.99; 2027-01-01: 1.99
11L | 11L_W9_STP | Diluted_Stoping_Tonnes | 2026-09-01: 1947; 2026-10-01: 2022; 2026-11-01: 357
11L | 11L_W9_STP | Au_dil | 2026-09-01: 1.8; 2026-10-01: 1.8; 2026-11-01: 1.8
11L Total | 11L Total | Diluted_Stoping_Tonnes | 2026-09-01: 2880; 2026-10-01: 7791; 2026-11-01: 15826; 2026-12-01: 17380; 2027-01-01: 16849; 2027-02-01: 13305; 2027-03-01: 7484; 2027-04-01: 5972; 2027-05-01: 5393; 2027-06-01: 4266; 2027-07-01: 2150; 2027-08-01: 1798; 2027-09-01: 1679
11L Total | 11L Total | Au_dil | 2026-09-01: 1.81; 2026-10-01: 2.2; 2026-11-01: 2.91; 2026-12-01: 2.71; 2027-01-01: 2.61; 2027-02-01: 2.62; 2027-03-01: 2.41; 2027-04-01: 2.38; 2027-05-01: 2.36; 2027-06-01: 2.05; 2027-07-01: 1.94; 2027-08-01: 1.94; 2027-09-01: 1.94
11L_A | 11L_A_E1A_STP | Diluted_Stoping_Tonnes | 2027-04-01: 1872; 2027-05-01: 1798; 2027-06-01: 1393
11L_A | 11L_A_E1A_STP | Au_dil | 2027-04-01: 2.91; 2027-05-01: 2.91; 2027-06-01: 2.91
11L_A | 11L_A_E1B_STP | Diluted_Stoping_Tonnes | 2027-02-01: 1798; 2027-03-01: 1798; 2027-04-01: 1224
11L_A | 11L_A_E1B_STP | Au_dil | 2027-02-01: 3.39; 2027-03-01: 3.39; 2027-04-01: 3.39
11L_A | 11L_A_W17A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1742
11L_A | 11L_A_W17A_STP | Au_dil | 2027-07-01: 2.87
11L_A | 11L_A_W17B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1659
11L_A | 11L_A_W17B_STP | Au_dil | 2027-07-01: 3.97
11L_A | 11L_A_W18A_STP | Diluted_Stoping_Tonnes | 2027-05-01: 1798; 2027-06-01: 1521
11L_A | 11L_A_W18A_STP | Au_dil | 2027-05-01: 3.97; 2027-06-01: 3.97
11L_A | 11L_A_W18B_STP | Diluted_Stoping_Tonnes | 2027-03-01: 1798; 2027-04-01: 1117
11L_A | 11L_A_W18B_STP | Au_dil | 2027-03-01: 3.97; 2027-04-01: 3.97
11L_A | 11L_A_W20A_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1678
11L_A | 11L_A_W20A_STP | Au_dil | 2027-06-01: 3.66
11L_A | 11L_A_W20B_STP | Diluted_Stoping_Tonnes | 2027-04-01: 689; 2027-05-01: 1798; 2027-06-01: 276
11L_A | 11L_A_W20B_STP | Au_dil | 2027-04-01: 3.97; 2027-05-01: 3.97; 2027-06-01: 3.97
11L_A | 11L_A_W3A_STP | Diluted_Stoping_Tonnes | 2027-05-01: 1221; 2027-06-01: 1947; 2027-07-01: 90
11L_A | 11L_A_W3A_STP | Au_dil | 2027-05-01: 3.97; 2027-06-01: 3.97; 2027-07-01: 3.97
11L_A | 11L_A_W3B_STP | Diluted_Stoping_Tonnes | 2027-01-01: 1255; 2027-02-01: 588
11L_A | 11L_A_W3B_STP | Au_dil | 2027-01-01: 3.97; 2027-02-01: 3.97
11L_A | 11L_A_W5A_STP | Diluted_Stoping_Tonnes | 2027-04-01: 1872; 2027-05-01: 781
11L_A | 11L_A_W5A_STP | Au_dil | 2027-04-01: 2.17; 2027-05-01: 2.17
11L_A | 11L_A_W8A_STP | Diluted_Stoping_Tonnes | 2027-04-01: 1872; 2027-05-01: 1607
11L_A | 11L_A_W8A_STP | Au_dil | 2027-04-01: 2.22; 2027-05-01: 2.22
11L_A | 11L_A_W8B_STP | Diluted_Stoping_Tonnes | 2027-03-01: 1798; 2027-04-01: 1873; 2027-05-01: 1047
11L_A | 11L_A_W8B_STP | Au_dil | 2027-03-01: 2.87; 2027-04-01: 2.87; 2027-05-01: 2.87
11L_A Total | 11L_A Total | Diluted_Stoping_Tonnes | 2027-01-01: 1255; 2027-02-01: 2385; 2027-03-01: 5393; 2027-04-01: 10519; 2027-05-01: 10049; 2027-06-01: 6816; 2027-07-01: 3491
11L_A Total | 11L_A Total | Au_dil | 2027-01-01: 3.97; 2027-02-01: 3.53; 2027-03-01: 3.41; 2027-04-01: 2.89; 2027-05-01: 3.25; 2027-06-01: 3.68; 2027-07-01: 3.42
12L | 12L_W10A_STP | Diluted_Stoping_Tonnes | 2027-04-01: 1873; 2027-05-01: 1798; 2027-06-01: 1025
12L | 12L_W10A_STP | Au_dil | 2027-04-01: 2.3; 2027-05-01: 2.3; 2027-06-01: 2.3
12L | 12L_W10B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1187
12L | 12L_W10B_STP | Au_dil | 2027-06-01: 3.65; 2027-07-01: 3.65; 2027-08-01: 3.65
12L | 12L_W12A_STP | Diluted_Stoping_Tonnes | 2027-03-01: 1798; 2027-04-01: 1024
12L | 12L_W12A_STP | Au_dil | 2027-03-01: 3.18; 2027-04-01: 3.18
12L | 12L_W12B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1947; 2027-07-01: 1674
12L | 12L_W12B_STP | Au_dil | 2027-06-01: 2.09; 2027-07-01: 2.09
12L | 12L_W15A_STP | Diluted_Stoping_Tonnes | 2027-05-01: 1017
12L | 12L_W15A_STP | Au_dil | 2027-05-01: 2.9
12L | 12L_W15B_STP | Diluted_Stoping_Tonnes | 2027-03-01: 386; 2027-04-01: 1307
12L | 12L_W15B_STP | Au_dil | 2027-03-01: 2.77; 2027-04-01: 2.77
12L | 12L_W16A_STP | Diluted_Stoping_Tonnes | 2027-05-01: 1798; 2027-06-01: 1947; 2027-07-01: 220
12L | 12L_W16A_STP | Au_dil | 2027-05-01: 1.85; 2027-06-01: 1.85; 2027-07-01: 1.85
12L | 12L_W16B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1287
12L | 12L_W16B_STP | Au_dil | 2027-06-01: 3.97; 2027-07-01: 3.97; 2027-08-01: 3.97
12L | 12L_W18_STP | Diluted_Stoping_Tonnes | 2027-03-01: 963
12L | 12L_W18_STP | Au_dil | 2027-03-01: 3.5
12L | 12L_W1A_STP | Diluted_Stoping_Tonnes | 2027-04-01: 1872; 2027-05-01: 921
12L | 12L_W1A_STP | Au_dil | 2027-04-01: 3.97; 2027-05-01: 3.97
12L | 12L_W1B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 2022; 2027-08-01: 1570
12L | 12L_W1B_STP | Au_dil | 2027-07-01: 1.88; 2027-08-01: 1.88
12L | 12L_W3A_STP | Diluted_Stoping_Tonnes | 2027-02-01: 1432
12L | 12L_W3A_STP | Au_dil | 2027-02-01: 3.97
12L | 12L_W3B_STP | Diluted_Stoping_Tonnes | 2027-06-01: 242; 2027-07-01: 2022; 2027-08-01: 300
12L | 12L_W3B_STP | Au_dil | 2027-06-01: 3.97; 2027-07-01: 3.97; 2027-08-01: 3.97
12L | 12L_W5A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1962
12L | 12L_W5A_STP | Au_dil | 2027-07-01: 3.89
12L | 12L_W5B_STP | Diluted_Stoping_Tonnes | 2027-05-01: 1798; 2027-06-01: 215
12L | 12L_W5B_STP | Au_dil | 2027-05-01: 3.43; 2027-06-01: 3.43
12L | 12L_W9A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 1015
12L | 12L_W9A_STP | Au_dil | 2027-07-01: 3.03
12L | 12L_W9B_STP | Diluted_Stoping_Tonnes | 2027-02-01: 258; 2027-03-01: 1628
12L | 12L_W9B_STP | Au_dil | 2027-02-01: 3.97; 2027-03-01: 3.97
12L Total | 12L Total | Diluted_Stoping_Tonnes | 2027-02-01: 1690; 2027-03-01: 4774; 2027-04-01: 6075; 2027-05-01: 7331; 2027-06-01: 9271; 2027-07-01: 12960; 2027-08-01: 4344
12L Total | 12L Total | Au_dil | 2027-02-01: 3.97; 2027-03-01: 3.48; 2027-04-01: 3.06; 2027-05-01: 2.76; 2027-06-01: 2.86; 2027-07-01: 3.23; 2027-08-01: 3.13
12L_A | 12L_A_E1_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1947; 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 70
12L_A | 12L_A_E1_STP | Au_dil | 2027-06-01: 2.19; 2027-07-01: 2.19; 2027-08-01: 2.19; 2027-09-01: 2.19; 2027-10-01: 2.19; 2027-11-01: 2.19
12L_A | 12L_A_W1_STP | Diluted_Stoping_Tonnes | 2027-06-01: 1947; 2027-07-01: 135
12L_A | 12L_A_W1_STP | Au_dil | 2027-06-01: 3.97; 2027-07-01: 3.97
12L_A | 12L_A_W11A_STP | Diluted_Stoping_Tonnes | 2027-08-01: 973
12L_A | 12L_A_W11A_STP | Au_dil | 2027-08-01: 2.47
12L_A | 12L_A_W11B_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 113
12L_A | 12L_A_W11B_STP | Au_dil | 2027-08-01: 2.26; 2027-09-01: 2.26
12L_A | 12L_A_W12A_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1470
12L_A | 12L_A_W12A_STP | Au_dil | 2028-02-01: 2.2; 2028-03-01: 2.2
12L_A | 12L_A_W12B_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 544
12L_A | 12L_A_W12B_STP | Au_dil | 2028-02-01: 1.73; 2028-03-01: 1.73; 2028-04-01: 1.73
12L_A | 12L_A_W14A_STP | Diluted_Stoping_Tonnes | 2028-03-01: 1798; 2028-04-01: 1601
12L_A | 12L_A_W14A_STP | Au_dil | 2028-03-01: 2.41; 2028-04-01: 2.41
12L_A | 12L_A_W14B_STP | Diluted_Stoping_Tonnes | 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 197
12L_A | 12L_A_W14B_STP | Au_dil | 2028-03-01: 2.25; 2028-04-01: 2.25; 2028-05-01: 2.25
12L_A | 12L_A_W18A_STP | Diluted_Stoping_Tonnes | 2028-04-01: 527
12L_A | 12L_A_W18A_STP | Au_dil | 2028-04-01: 2.6
12L_A | 12L_A_W18B_STP | Diluted_Stoping_Tonnes | 2028-04-01: 621
12L_A | 12L_A_W18B_STP | Au_dil | 2028-04-01: 1.79
12L_A | 12L_A_W4A_STP | Diluted_Stoping_Tonnes | 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1195
12L_A | 12L_A_W4A_STP | Au_dil | 2027-07-01: 3.02; 2027-08-01: 3.02; 2027-09-01: 3.02
12L_A | 12L_A_W4B_STP | Diluted_Stoping_Tonnes | 2027-07-01: 2022; 2027-08-01: 1798; 2027-09-01: 1437
12L_A | 12L_A_W4B_STP | Au_dil | 2027-07-01: 2.9; 2027-08-01: 2.9; 2027-09-01: 2.9
12L_A | 12L_A_W5_STP | Diluted_Stoping_Tonnes | 2027-07-01: 734
12L_A | 12L_A_W5_STP | Au_dil | 2027-07-01: 3.27
12L_A | 12L_A_W6_STP | Diluted_Stoping_Tonnes | 2027-07-01: 82; 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 590
12L_A | 12L_A_W6_STP | Au_dil | 2027-07-01: 3.84; 2027-08-01: 3.84; 2027-09-01: 3.84; 2027-10-01: 3.84
12L_A Total | 12L_A Total | Diluted_Stoping_Tonnes | 2027-06-01: 3895; 2027-07-01: 7018; 2027-08-01: 9961; 2027-09-01: 6640; 2027-10-01: 2537; 2027-11-01: 70; 2028-02-01: 3595; 2028-03-01: 6863; 2028-04-01: 5090; 2028-05-01: 197
12L_A Total | 12L_A Total | Au_dil | 2027-06-01: 3.08; 2027-07-01: 2.8; 2027-08-01: 2.8; 2027-09-01: 2.98; 2027-10-01: 2.57; 2027-11-01: 2.19; 2028-02-01: 1.97; 2028-03-01: 2.15; 2028-04-01: 2.23; 2028-05-01: 2.25
13L | 13L_E1A_STP | Diluted_Stoping_Tonnes | 2027-11-01: 1947; 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1872; 2028-06-01: 1947; 2028-07-01: 1947; 2028-08-01: 1872; 2028-09-01: 1947; 2028-10-01: 763
13L | 13L_E1A_STP | Au_dil | 2027-11-01: 2.09; 2027-12-01: 2.09; 2028-01-01: 2.09; 2028-02-01: 2.09; 2028-03-01: 2.09; 2028-04-01: 2.09; 2028-05-01: 2.09; 2028-06-01: 2.09; 2028-07-01: 2.09; 2028-08-01: 2.09; 2028-09-01: 2.09; 2028-10-01: 2.09
13L | 13L_E1B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1873; 2028-01-01: 1873; 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1873; 2028-06-01: 1947; 2028-07-01: 1947; 2028-08-01: 1873; 2028-09-01: 1947; 2028-10-01: 185
13L | 13L_E1B_STP | Au_dil | 2027-10-01: 2.42; 2027-11-01: 2.42; 2027-12-01: 2.42; 2028-01-01: 2.42; 2028-02-01: 2.42; 2028-03-01: 2.42; 2028-04-01: 2.42; 2028-05-01: 2.42; 2028-06-01: 2.42; 2028-07-01: 2.42; 2028-08-01: 2.42; 2028-09-01: 2.42; 2028-10-01: 2.42
13L | 13L_W10_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1873; 2028-01-01: 1757
13L | 13L_W10_STP | Au_dil | 2027-12-01: 3.97; 2028-01-01: 3.97
13L | 13L_W12_STP | Diluted_Stoping_Tonnes | 2027-11-01: 1947; 2027-12-01: 1873; 2028-01-01: 418
13L | 13L_W12_STP | Au_dil | 2027-11-01: 2.14; 2027-12-01: 2.14; 2028-01-01: 2.14
13L | 13L_W1A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1442; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 882
13L | 13L_W1A_STP | Au_dil | 2027-09-01: 3.7; 2027-10-01: 3.7; 2027-11-01: 3.7; 2027-12-01: 3.7
13L | 13L_W1B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1148
13L | 13L_W1B_STP | Au_dil | 2027-10-01: 3.97; 2027-11-01: 3.97; 2027-12-01: 3.97
13L | 13L_W4A_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 840
13L | 13L_W4A_STP | Au_dil | 2027-08-01: 2.08; 2027-09-01: 2.08; 2027-10-01: 2.08; 2027-11-01: 2.08
13L | 13L_W4B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1946
13L | 13L_W4B_STP | Au_dil | 2027-09-01: 1.91; 2027-10-01: 1.91; 2027-11-01: 1.91
13L | 13L_W6A_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1748
13L | 13L_W6A_STP | Au_dil | 2027-10-01: 2.33
13L | 13L_W6B_STP | Diluted_Stoping_Tonnes | 2028-01-01: 1872; 2028-02-01: 578
13L | 13L_W6B_STP | Au_dil | 2028-01-01: 2.95; 2028-02-01: 2.95
13L | 13L_W8A_STP | Diluted_Stoping_Tonnes | 2028-01-01: 1702
13L | 13L_W8A_STP | Au_dil | 2028-01-01: 3.83
13L | 13L_W8B_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1350
13L | 13L_W8B_STP | Au_dil | 2028-02-01: 2.93
13L | 13L_W9_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1727
13L | 13L_W9_STP | Au_dil | 2027-09-01: 2.1
13L Total | 13L Total | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 7064; 2027-10-01: 11485; 2027-11-01: 12523; 2027-12-01: 9520; 2028-01-01: 9494; 2028-02-01: 5523; 2028-03-01: 3595; 2028-04-01: 3595; 2028-05-01: 3745; 2028-06-01: 3895; 2028-07-01: 3895; 2028-08-01: 3745; 2028-09-01: 3895; 2028-10-01: 948
13L Total | 13L Total | Au_dil | 2027-08-01: 2.08; 2027-09-01: 2.37; 2027-10-01: 2.74; 2027-11-01: 2.66; 2027-12-01: 2.91; 2028-01-01: 2.99; 2028-02-01: 2.5; 2028-03-01: 2.26; 2028-04-01: 2.26; 2028-05-01: 2.26; 2028-06-01: 2.26; 2028-07-01: 2.26; 2028-08-01: 2.26; 2028-09-01: 2.26; 2028-10-01: 2.16
13L_A | 13L_A_E1A_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1872; 2028-06-01: 1947; 2028-07-01: 1947; 2028-08-01: 1872; 2028-09-01: 500
13L_A | 13L_A_E1A_STP | Au_dil | 2027-12-01: 3.34; 2028-01-01: 3.34; 2028-02-01: 3.34; 2028-03-01: 3.34; 2028-04-01: 3.34; 2028-05-01: 3.34; 2028-06-01: 3.34; 2028-07-01: 3.34; 2028-08-01: 3.34; 2028-09-01: 3.34
13L_A | 13L_A_E1B_STP | Diluted_Stoping_Tonnes | 2028-01-01: 1873; 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1873; 2028-06-01: 1947; 2028-07-01: 1947; 2028-08-01: 1246
13L_A | 13L_A_E1B_STP | Au_dil | 2028-01-01: 3.97; 2028-02-01: 3.97; 2028-03-01: 3.97; 2028-04-01: 3.97; 2028-05-01: 3.97; 2028-06-01: 3.97; 2028-07-01: 3.97; 2028-08-01: 3.97
13L_A | 13L_A_E4A_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1872; 2028-01-01: 1697
13L_A | 13L_A_E4A_STP | Au_dil | 2027-10-01: 2.69; 2027-11-01: 2.69; 2027-12-01: 2.69; 2028-01-01: 2.69
13L_A | 13L_A_E4B_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1333
13L_A | 13L_A_E4B_STP | Au_dil | 2027-08-01: 3.31; 2027-09-01: 3.31; 2027-10-01: 3.31; 2027-11-01: 3.31
13L_A | 13L_A_E5A_STP | Diluted_Stoping_Tonnes | 2027-11-01: 767
13L_A | 13L_A_E5A_STP | Au_dil | 2027-11-01: 3.59
13L_A | 13L_A_E5B_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1835
13L_A | 13L_A_E5B_STP | Au_dil | 2027-09-01: 3.51
13L_A | 13L_A_W10A_STP | Diluted_Stoping_Tonnes | 2028-01-01: 1327; 2028-02-01: 1798; 2028-03-01: 1185
13L_A | 13L_A_W10A_STP | Au_dil | 2028-01-01: 1.66; 2028-02-01: 1.66; 2028-03-01: 1.66
13L_A | 13L_A_W10B_STP | Diluted_Stoping_Tonnes | 2027-11-01: 1947; 2027-12-01: 1872; 2028-01-01: 1369
13L_A | 13L_A_W10B_STP | Au_dil | 2027-11-01: 2.03; 2027-12-01: 2.03; 2028-01-01: 2.03
13L_A | 13L_A_W12A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1002
13L_A | 13L_A_W12A_STP | Au_dil | 2027-09-01: 3.03; 2027-10-01: 3.03; 2027-11-01: 3.03
13L_A | 13L_A_W12B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 881
13L_A | 13L_A_W12B_STP | Au_dil | 2027-10-01: 2.94; 2027-11-01: 2.94; 2027-12-01: 2.94
13L_A | 13L_A_W14A_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1222
13L_A | 13L_A_W14A_STP | Au_dil | 2028-02-01: 3.8; 2028-03-01: 3.8
13L_A | 13L_A_W14B_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 692
13L_A | 13L_A_W14B_STP | Au_dil | 2028-02-01: 3.6; 2028-03-01: 3.6
13L_A | 13L_A_W16A_STP | Diluted_Stoping_Tonnes | 2028-03-01: 732; 2028-04-01: 591
13L_A | 13L_A_W16A_STP | Au_dil | 2028-03-01: 3.48; 2028-04-01: 3.48
13L_A | 13L_A_W16B_STP | Diluted_Stoping_Tonnes | 2028-04-01: 1798; 2028-05-01: 1451
13L_A | 13L_A_W16B_STP | Au_dil | 2028-04-01: 2.42; 2028-05-01: 2.42
13L_A | 13L_A_W1A_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1690
13L_A | 13L_A_W1A_STP | Au_dil | 2027-09-01: 3.72; 2027-10-01: 3.72; 2027-11-01: 3.72; 2027-12-01: 3.72
13L_A | 13L_A_W1B_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 1798; 2028-03-01: 1381
13L_A | 13L_A_W1B_STP | Au_dil | 2027-12-01: 3.33; 2028-01-01: 3.33; 2028-02-01: 3.33; 2028-03-01: 3.33
13L_A | 13L_A_W6A_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1947; 2027-11-01: 1279
13L_A | 13L_A_W6A_STP | Au_dil | 2027-10-01: 3.97; 2027-11-01: 3.97
13L_A | 13L_A_W6B_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1254
13L_A | 13L_A_W6B_STP | Au_dil | 2028-02-01: 3.97; 2028-03-01: 3.97
13L_A | 13L_A_W8_STP | Diluted_Stoping_Tonnes | 2027-12-01: 395; 2028-01-01: 1872; 2028-02-01: 385
13L_A | 13L_A_W8_STP | Au_dil | 2027-12-01: 3.97; 2028-01-01: 3.97; 2028-02-01: 3.97
13L_A | 13L_A_W9_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 818
13L_A | 13L_A_W9_STP | Au_dil | 2027-08-01: 3.97; 2027-09-01: 3.97
13L_A Total | 13L_A Total | Diluted_Stoping_Tonnes | 2027-08-01: 3595; 2027-09-01: 8496; 2027-10-01: 11684; 2027-11-01: 12170; 2027-12-01: 10457; 2028-01-01: 11883; 2028-02-01: 12968; 2028-03-01: 10062; 2028-04-01: 5984; 2028-05-01: 5196; 2028-06-01: 3895; 2028-07-01: 3895; 2028-08-01: 3119; 2028-09-01: 500
13L_A Total | 13L_A Total | Au_dil | 2027-08-01: 3.64; 2027-09-01: 3.45; 2027-10-01: 3.28; 2027-11-01: 3.08; 2027-12-01: 3.04; 2028-01-01: 3.11; 2028-02-01: 3.4; 2028-03-01: 3.42; 2028-04-01: 3.27; 2028-05-01: 3.31; 2028-06-01: 3.66; 2028-07-01: 3.66; 2028-08-01: 3.59; 2028-09-01: 3.34
14L | 14L_W1A_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 573
14L | 14L_W1A_STP | Au_dil | 2028-02-01: 3.59; 2028-03-01: 3.59; 2028-04-01: 3.59
14L | 14L_W1B_STP | Diluted_Stoping_Tonnes | 2028-02-01: 1798; 2028-03-01: 1798; 2028-04-01: 1169
14L | 14L_W1B_STP | Au_dil | 2028-02-01: 3.6; 2028-03-01: 3.6; 2028-04-01: 3.6
14L | 14L_W8A_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1873; 2028-01-01: 402
14L | 14L_W8A_STP | Au_dil | 2027-12-01: 3.97; 2028-01-01: 3.97
14L | 14L_W8B_STP | Diluted_Stoping_Tonnes | 2027-10-01: 1259; 2027-11-01: 1588
14L | 14L_W8B_STP | Au_dil | 2027-10-01: 3.97; 2027-11-01: 3.97
14L Total | 14L Total | Diluted_Stoping_Tonnes | 2027-10-01: 1259; 2027-11-01: 1588; 2027-12-01: 1873; 2028-01-01: 402; 2028-02-01: 3595; 2028-03-01: 3595; 2028-04-01: 1742
14L Total | 14L Total | Au_dil | 2027-10-01: 3.97; 2027-11-01: 3.97; 2027-12-01: 3.97; 2028-01-01: 3.97; 2028-02-01: 3.59; 2028-03-01: 3.59; 2028-04-01: 3.6
14L_A | 14L_A_W1A_STP | Diluted_Stoping_Tonnes | 2028-02-01: 312; 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1797
14L_A | 14L_A_W1A_STP | Au_dil | 2028-02-01: 3.81; 2028-03-01: 3.81; 2028-04-01: 3.81; 2028-05-01: 3.81
14L_A | 14L_A_W1B_STP | Diluted_Stoping_Tonnes | 2028-03-01: 1798; 2028-04-01: 1798; 2028-05-01: 1873; 2028-06-01: 577
14L_A | 14L_A_W1B_STP | Au_dil | 2028-03-01: 3.61; 2028-04-01: 3.61; 2028-05-01: 3.61; 2028-06-01: 3.61
14L_A | 14L_A_W4A_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 1798; 2028-03-01: 1059
14L_A | 14L_A_W4A_STP | Au_dil | 2027-12-01: 1.86; 2028-01-01: 1.86; 2028-02-01: 1.86; 2028-03-01: 1.86
14L_A | 14L_A_W4B_STP | Diluted_Stoping_Tonnes | 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 1798; 2028-03-01: 1193
14L_A | 14L_A_W4B_STP | Au_dil | 2027-12-01: 1.97; 2028-01-01: 1.97; 2028-02-01: 1.97; 2028-03-01: 1.97
14L_A | 14L_A_W7A_STP | Diluted_Stoping_Tonnes | 2028-01-01: 601
14L_A | 14L_A_W7A_STP | Au_dil | 2028-01-01: 3.97
14L_A | 14L_A_W7B_STP | Diluted_Stoping_Tonnes | 2027-11-01: 1203
14L_A | 14L_A_W7B_STP | Au_dil | 2027-11-01: 3.91
14L_A | 14L_A_W8A_STP | Diluted_Stoping_Tonnes | 2027-11-01: 1010; 2027-12-01: 1873; 2028-01-01: 1506
14L_A | 14L_A_W8A_STP | Au_dil | 2027-11-01: 1.95; 2027-12-01: 1.95; 2028-01-01: 1.95
14L_A | 14L_A_W8B_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1486; 2027-09-01: 1947; 2027-10-01: 1408
14L_A | 14L_A_W8B_STP | Au_dil | 2027-08-01: 2.28; 2027-09-01: 2.28; 2027-10-01: 2.28
14L_A Total | 14L_A Total | Diluted_Stoping_Tonnes | 2027-08-01: 1486; 2027-09-01: 1947; 2027-10-01: 1408; 2027-11-01: 2213; 2027-12-01: 5618; 2028-01-01: 5853; 2028-02-01: 3907; 2028-03-01: 5847; 2028-04-01: 3595; 2028-05-01: 3670; 2028-06-01: 577
14L_A Total | 14L_A Total | Au_dil | 2027-08-01: 2.28; 2027-09-01: 2.28; 2027-10-01: 2.28; 2027-11-01: 3.01; 2027-12-01: 1.93; 2028-01-01: 2.14; 2028-02-01: 2.07; 2028-03-01: 3.02; 2028-04-01: 3.71; 2028-05-01: 3.71; 2028-06-01: 3.61
15L | 15L_W1_STP | Diluted_Stoping_Tonnes | 2028-04-01: 1798; 2028-05-01: 1873; 2028-06-01: 1947; 2028-07-01: 166
15L | 15L_W1_STP | Au_dil | 2028-04-01: 2.31; 2028-05-01: 2.31; 2028-06-01: 2.31; 2028-07-01: 2.31
15L | 15L_W10_STP | Diluted_Stoping_Tonnes | 2027-09-01: 1947; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 374
15L | 15L_W10_STP | Au_dil | 2027-09-01: 3.97; 2027-10-01: 3.97; 2027-11-01: 3.97; 2027-12-01: 3.97; 2028-01-01: 3.97; 2028-02-01: 3.97
15L | 15L_W8_STP | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 791
15L | 15L_W8_STP | Au_dil | 2027-08-01: 3.97; 2027-09-01: 3.97
15L Total | 15L Total | Diluted_Stoping_Tonnes | 2027-08-01: 1798; 2027-09-01: 2738; 2027-10-01: 1947; 2027-11-01: 1947; 2027-12-01: 1872; 2028-01-01: 1872; 2028-02-01: 374; 2028-04-01: 1798; 2028-05-01: 1873; 2028-06-01: 1947; 2028-07-01: 166
15L Total | 15L Total | Au_dil | 2027-08-01: 3.97; 2027-09-01: 3.97; 2027-10-01: 3.97; 2027-11-01: 3.97; 2027-12-01: 3.97; 2028-01-01: 3.97; 2028-02-01: 3.97; 2028-04-01: 2.31; 2028-05-01: 2.31; 2028-06-01: 2.31; 2028-07-01: 2.31
Grand Total | Grand Total | Diluted_Stoping_Tonnes | 10324 | 10446 | 6167 | 4681 | 27314 | 19812 | 27066 | 30752 | 21201 | 20373 | 21649 | 18501 | 21708 | 22722 | 21246 | 25191 | 33338 | 31212 | 29963 | 32514 | 28715 | 29963 | 31212 | 29963 | 32460 | 33708 | 29963 | 32460 | 33708 | 31211 | 29963 | 31211 | 29963 | 29963 | 31212 | 29963 | 32460 | 33708 | 29963 | 32460 | 32460 | 32460 | 31211 | 31211 | 29963 | 29963 | 21804 | 14681 | 10314 | 7955 | 6864 | 4394 | 948
Grand Total | Grand Total | Au_dil | 1.56 | 1.77 | 2.27 | 1.49 | 1.82 | 1.98 | 2.15 | 2.13 | 1.97 | 2.12 | 2.46 | 2.58 | 2.55 | 2.4 | 2.48 | 2.66 | 2.71 | 2.62 | 2.46 | 2.43 | 2.69 | 2.82 | 2.93 | 2.83 | 2.86 | 2.75 | 2.63 | 2.64 | 2.3 | 2.32 | 2.33 | 2.33 | 2.43 | 2.51 | 2.49 | 2.58 | 2.75 | 2.9 | 2.82 | 2.84 | 2.96 | 2.93 | 2.84 | 2.88 | 2.92 | 2.93 | 2.88 | 3 | 2.87 | 2.94 | 2.86 | 2.38 | 2.16

## Developed Reserve Balance
 | time axis 2024-06-01 to 2028-09-01
1L | 1L_W24_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W24_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52 | 0.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W27_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13487 | 10454 | 7758 | 4837 | 1804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W27_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W28_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16050 | 14028 | 12156 | 10358 | 8486 | 6688 | 4890 | 3018 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W28_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W30_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4138 | 4138 | 2988 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L | 1L_W30_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.71 | 3.71 | 3.71 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L Total | 1L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13487 | 10454 | 7758 | 20887 | 15832 | 12156 | 10358 | 8486 | 6688 | 4890 | 7156 | 5358 | 2988 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1L Total | 1L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52 | 0.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0.47 | 0.47 | 0.38547 | 0.37253 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 2.2972 | 2.9472 | 3.71 | 3.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_E8_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_E8_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W23_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 11200 | 11200 | 10542 | 7846 | 4925 | 2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W23_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W24A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 5143 | 5143 | 3443 | 1496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W24A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W24B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 7459 | 7459 | 7459 | 5512 | 3789 | 1991 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W24B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W26A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3243 | 3243 | 3075 | 1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W26A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.58 | 1.58 | 1.58 | 1.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W26B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3101 | 3101 | 2843 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W26B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W28A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14789 | 14789 | 13443 | 10522 | 7489 | 4680 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W28A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W28B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15215 | 15215 | 12883 | 9850 | 7041 | 4345 | 1424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 3L_W28B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 | 2.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L Total | 3L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 11200 | 23802 | 23144 | 18748 | 11933 | 6130 | 1991 | 3362 | 6344 | 20965 | 33900 | 29703 | 23405 | 17339 | 11721 | 6329 | 1424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L Total | 3L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 2.55 | 1.9118 | 1.8936 | 1.8984 | 1.9472 | 2.037 | 1.72 | 1.585 | 1.8831 | 2.3418 | 2.5177 | 2.5696 | 2.585 | 2.5868 | 2.5901 | 2.5987 | 2.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W10B_STP | Diluted_Stoping_Tonnes | -2809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W10B_STP | Au_dil | 2.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W11A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W11A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W11B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W11B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W13B_STP | Diluted_Stoping_Tonnes | -1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W13B_STP | Au_dil | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15A_STP | Diluted_Stoping_Tonnes | -1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15A_STP | Au_dil | 1.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15C_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W15C_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16A_STP | Diluted_Stoping_Tonnes | -1897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16A_STP | Au_dil | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16B_STP | Diluted_Stoping_Tonnes | -1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16B_STP | Au_dil | 2.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16C_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W16C_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W23_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 8489 | 5456 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | 4L_W23_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 1.81 | 1.81 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L Total | 4L Total | Diluted_Stoping_Tonnes | -10323 | 0 | 0 | 0 | 0 | 0 | 8489 | 5456 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L Total | 4L Total | Au_dil | 1.5582 | 0 | 0 | 0 | 0 | 0 | 1.81 | 1.81 | 1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3930 | 2058 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.33 | 3.33 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W11A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W11A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.94 | 2.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W11B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2645 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W11B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.89 | 1.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5097 | 3225 | 1427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 1.6 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4902 | 4902 | 4902 | 4902 | 3029 | 1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5174 | 5174 | 5174 | 5174 | 3302 | 1504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.28 | 3.28 | 3.28 | 3.28 | 3.28 | 3.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5058 | 5058 | 5058 | 3185 | 1387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W25A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3267 | 1469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W25A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.23 | 3.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W25B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5386 | 3439 | 1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W25B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W5A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 2036 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W5A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 1.82 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W5B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W5B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W7A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W7A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W7B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W7B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4753 | 4041 | 2243 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 3.3 | 3.3 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4495 | 3770 | 1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 5L_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L Total | 5L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 2149 | 351 | 5764 | 4225 | 14201 | 9356 | 3144 | 0 | 3267 | 6855 | 3439 | 6514 | 3225 | 11503 | 15134 | 15134 | 15134 | 9516 | 4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L Total | 5L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 1.8137 | 1.82 | 2.8141 | 3.192 | 3.2489 | 3.1583 | 3.1469 | 0 | 3.23 | 3.8114 | 3.97 | 2.1155 | 1.6 | 2.2704 | 2.5106 | 2.5106 | 2.5106 | 2.5209 | 2.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_E1_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 41279 | 38358 | 35774 | 33078 | 30269 | 27348 | 24539 | 21506 | 18810 | 15889 | 12856 | 10047 | 7351 | 4430 | 1846 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
6L | 6L_E1_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83
6L | 6L_W13_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 2154 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W13_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 3.63 | 3.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 2428 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.87 | 2.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 4322 | 4322 | 3080 | 1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 2.45 | 2.45 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W19A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3553 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W19A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.84 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W19B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4053 | 2031 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W19B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 3.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W2_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28073 | 25264 | 22343 | 19534 | 16501 | 13805 | 10884 | 7851 | 5042 | 2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W2_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W27_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W27_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W28_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W28_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W4_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9196 | 7323 | 5376 | 3503 | 1481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W4_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W6_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 5380 | 3433 | 1710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W6_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.0213 | 1.4322 | 1.5251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W8_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W8_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 1.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 3791 | 1844 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 6L_W9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.7 | 2.7 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L Total | 6L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 61161 | 48645 | 40685 | 71629 | 62856 | 59768 | 53309 | 41519 | 32848 | 26773 | 20707 | 15089 | 9697 | 4430 | 1846 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
6L Total | 6L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 2.7165 | 2.6965 | 2.746 | 2.5655 | 2.5721 | 2.6203 | 2.6403 | 2.6265 | 2.6141 | 2.6186 | 2.6328 | 2.6562 | 2.7042 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83 | 2.83
6L_A | 6L_A_E4_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2831 | 2817 | 2817 | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_E4_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 1.94 | 1.94 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_E5_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3272 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_E5_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.22 | 3.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W11_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W11_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W12_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W12_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W14_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W14_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W19_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112 | 2199 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W19_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W2_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12990 | 10181 | 7485 | 4564 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W2_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.17 | 2.17 | 2.17 | 2.17 | 2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W26_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1874 | 975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W26_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W4_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381 | 1482 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W4_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.49 | 3.49 | 3.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W6_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2284 | 2284 | 1407 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W6_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.03 | 1.03 | 1.03 | 1.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W8_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10047 | 8426 | 6479 | 4457 | 2585 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A | 6L_A_W8_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A Total | 6L_A Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007 | 0 | 6356 | 4752 | 15886 | 11391 | 6987 | 17447 | 12766 | 11103 | 7381 | 4797 | 4291 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A Total | 6L_A Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.01 | 0 | 2.5616 | 2.5048 | 2.3909 | 2.4449 | 2.5256 | 2.2415 | 2.2267 | 2.1312 | 2.0822 | 2.0349 | 2.916 | 3.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W10A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3173 | 3173 | 3173 | 3173 | 3173 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W10A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 1.34 | 1.34 | 1.34 | 1.34 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3821 | 3821 | 3821 | 3821 | 3387 | 1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3908 | 3908 | 3908 | 3908 | 1961 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3605 | 3605 | 3011 | 1213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 | 2.88 | 2.88 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4993 | 2971 | 1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 3.61 | 3.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3694 | 1821 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.87 | 2.87 | 2.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17615 | 14582 | 11773 | 9077 | 6156 | 3572 | 876 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7L | 7L_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43
7L | 7L_W20A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1983 | 1983 | 1983 | 1983 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W20A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W20B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2679 | 2639 | 2639 | 841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W20B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W22A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4263 | 4263 | 4263 | 2390 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W22A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.53 | 2.53 | 2.53 | 2.53 | 2.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W22B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4258 | 4258 | 2385 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W22B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W6_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21485 | 18539 | 15730 | 11236 | 9383 | 9383 | 5788 | 3153 | 1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 7L_W6_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.16 | 2.098 | 2.0173 | 1.9522 | 1.8441 | 1.8441 | 1.7907 | 1.7411 | 1.7294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L Total | 7L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58600 | 54293 | 46319 | 37113 | 32945 | 29450 | 16211 | 7930 | 2536 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7L Total | 7L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4105 | 2.3885 | 2.3687 | 2.4169 | 2.4271 | 2.6353 | 2.6066 | 2.5081 | 2.3267 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43
8L | 8L_E5A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5483 | 5483 | 5483 | 5483 | 2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_E5A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_E5B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2899 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_E5B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 | 2.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W10A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303 | 3303 | 3303 | 3303 | 3303 | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W10A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3570 | 3570 | 3570 | 3570 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.55 | 2.55 | 2.55 | 2.55 | 2.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3959 | 3959 | 3959 | 3959 | 3959 | 2236 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4267 | 4267 | 4267 | 3265 | 1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.23 | 2.23 | 2.23 | 2.23 | 2.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3202 | 3202 | 3202 | 3202 | 1255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321 | 3321 | 3321 | 3321 | 3321 | 2597 | 799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4154 | 4154 | 4154 | 4154 | 4154 | 2431 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 3.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4448 | 4448 | 4448 | 4448 | 4448 | 2725 | 927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W20A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W20A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W20B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W20B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W22A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4610 | 4610 | 4610 | 2812 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W22A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W22B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5076 | 5076 | 4543 | 2671 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W22B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W24A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4619 | 4619 | 4619 | 2746 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W24A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W24B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950 | 5813 | 3941 | 2143 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W24B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W7A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842 | 842 | 842 | 842 | 842 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W7A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 | 3.44 | 3.44 | 3.44 | 3.44 | 3.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W7B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 602 | 602 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L | 8L_W7B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 | 2.88 | 2.88 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L Total | 8L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38606 | 38599 | 36549 | 40759 | 41692 | 31268 | 22028 | 10298 | 3964 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8L Total | 8L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9385 | 2.96 | 2.9737 | 2.963 | 3.1283 | 3.2454 | 3.2805 | 3.3605 | 3.4789 | 3.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_E5_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985 | 5985 | 5985 | 3289 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_E5_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_E9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2494 | 2494 | 2494 | 696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_E9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.29 | 2.29 | 2.29 | 2.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W1_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35788 | 35788 | 35788 | 33766 | 31968 | 30021 | 27999 | 26126 | 24328 | 22455 | 20657 | 18859 | 16986 | 15188 | 13241 | 11219 | 9421 | 7474 | 5527 | 3580 | 1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W1_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2818 | 2818 | 2818 | 2818 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3022 | 3022 | 3022 | 3022 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.68 | 2.68 | 2.68 | 2.68 | 2.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3048 | 3271 | 3271 | 1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3662 | 3662 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W20A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2403 | 2403 | 1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W20A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.53 | 3.53 | 3.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W20B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964 | 1964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W20B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W22A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3624 | 3624 | 3624 | 1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W22A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 3.01 | 3.01 | 3.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W22B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4093 | 4093 | 4093 | 2071 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W22B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W24_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126 | 1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W24_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.97 | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W4_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17674 | 17674 | 17674 | 15652 | 13854 | 11907 | 9885 | 8013 | 6215 | 4343 | 2545 | 747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W4_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2955 | 2955 | 2955 | 933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 9L_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L Total | 9L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2818 | 14319 | 17367 | 87789 | 84587 | 75297 | 54024 | 46095 | 41928 | 37884 | 34139 | 30543 | 26798 | 23202 | 19606 | 16986 | 15188 | 13241 | 11219 | 9421 | 7474 | 5527 | 3580 | 1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L Total | 9L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 2.2804 | 2.5769 | 2.2745 | 2.2968 | 2.236 | 1.933 | 1.8399 | 1.8341 | 1.8313 | 1.8282 | 1.8244 | 1.8194 | 1.8132 | 1.8046 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4158 | 4158 | 4158 | 4158 | 2211 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2613 | 2613 | 2613 | 2613 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E7A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3917 | 3917 | 2119 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E7A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E7B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3495 | 3495 | 1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E7B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1470 | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_E9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2532 | 2532 | 2532 | 2532 | 659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.21 | 3.21 | 3.21 | 3.21 | 3.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361 | 2361 | 2361 | 2361 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488 | 2488 | 2488 | 2488 | 1673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516 | 2516 | 2516 | 2516 | 2516 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31474 | 31474 | 31474 | 30450 | 28503 | 26481 | 24683 | 22736 | 20714 | 18842 | 17044 | 15172 | 13374 | 11576 | 9704 | 7906 | 5959 | 3937 | 2139 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27138 | 27138 | 27138 | 27138 | 25191 | 23169 | 21371 | 19424 | 17402 | 15529 | 13731 | 11858 | 10060 | 8262 | 6389 | 4591 | 2644 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W20A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3171 | 3171 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W20A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W20B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 2720 | 2684 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W20B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.58 | 3.58 | 3.58 | 3.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W22A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204 | 1204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W22A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W22B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2106 | 2106 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W22B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.49 | 2.49 | 2.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15313 | 15313 | 15313 | 13515 | 11568 | 9546 | 7673 | 5875 | 4002 | 2204 | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13457 | 13457 | 13457 | 12837 | 10890 | 8868 | 6996 | 5198 | 3326 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 2.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968 | 5968 | 4170 | 2223 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4245 | 4245 | 2298 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5081 | 5081 | 3283 | 1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.05 | 3.05 | 3.05 | 3.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5373 | 5373 | 3575 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 10L_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L Total | 10L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7536 | 7536 | 75280 | 75280 | 72592 | 102099 | 115295 | 115301 | 95957 | 73823 | 57007 | 49040 | 41848 | 34358 | 27166 | 20244 | 16093 | 12497 | 8603 | 4559 | 2139 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L Total | 10L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7146 | 3.7146 | 2.4642 | 2.4642 | 2.428 | 2.349 | 2.543 | 2.6296 | 2.5562 | 2.3615 | 2.1696 | 2.1581 | 2.163 | 2.1702 | 2.1808 | 2.198 | 2.2044 | 2.2086 | 2.217 | 2.2409 | 2.26 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11391 | 9492 | 7620 | 5822 | 3950 | 2152 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.77 | 2.77 | 2.77 | 2.77 | 2.77 | 2.77 | 2.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9509 | 9509 | 9509 | 7636 | 5838 | 4040 | 2167 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 | 3.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E7A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5761 | 5761 | 5761 | 5761 | 3963 | 2090 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E7A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E7B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6546 | 4673 | 2875 | 1002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_E7B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.46 | 2.46 | 2.46 | 2.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W10A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11213 | 11213 | 11213 | 11213 | 11213 | 9341 | 7543 | 5745 | 3873 | 2075 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W10A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16649 | 16649 | 16649 | 16649 | 16585 | 14712 | 12914 | 11116 | 9243 | 7445 | 5498 | 3476 | 1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4973 | 4040 | 2018 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 1.83 | 1.83 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4143 | 4143 | 4143 | 2271 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3361 | 3361 | 3361 | 1489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.76 | 3.76 | 3.76 | 3.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4345 | 2472 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.21 | 3.21 | 3.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7095 | 7095 | 7095 | 5223 | 3425 | 1553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7302 | 7302 | 5430 | 3632 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1790 | 1790 | 1790 | 1301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2519 | 2519 | 2519 | 2519 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4327 | 2380 | 358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 11L_W9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L Total | 11L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61831 | 77644 | 92101 | 76275 | 58892 | 42044 | 28739 | 21255 | 15283 | 9889 | 5626 | 3476 | 1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L Total | 11L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1906 | 2.4336 | 2.5704 | 2.5003 | 2.4379 | 2.3679 | 2.2506 | 2.1941 | 2.1198 | 1.9887 | 1.9402 | 1.94 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_E1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5063 | 5063 | 5063 | 5063 | 5063 | 5063 | 3191 | 1393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_E1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.91 | 2.91 | 2.91 | 2.91 | 2.91 | 2.91 | 2.91 | 2.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_E1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4819 | 4819 | 3021 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_E1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.39 | 3.39 | 3.39 | 3.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W17A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1742 | 1742 | 1742 | 1742 | 1742 | 1742 | 1742 | 1742 | 1742 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W17A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W17B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1659 | 1659 | 1659 | 1659 | 1659 | 1659 | 1659 | 1659 | 1659 | 1659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W17B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3319 | 3319 | 3319 | 3319 | 3319 | 3319 | 1521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2914 | 2914 | 2914 | 2914 | 1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W20A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678 | 1678 | 1678 | 1678 | 1678 | 1678 | 1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W20A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 3.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W20B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2763 | 2763 | 2763 | 2763 | 2074 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W20B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W3A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 2037 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W3A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W3B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W3B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W5A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2654 | 2654 | 2654 | 2654 | 2654 | 2654 | 782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W5A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.17 | 2.17 | 2.17 | 2.17 | 2.17 | 2.17 | 2.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3480 | 3480 | 3480 | 3480 | 3480 | 1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4717 | 4717 | 4717 | 4717 | 2919 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 11L_A_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A Total | 11L_A Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3401 | 11118 | 30484 | 39908 | 38653 | 36268 | 30874 | 20357 | 10306 | 3491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A Total | 11L_A Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4066 | 2.8853 | 3.1873 | 3.3021 | 3.2804 | 3.2638 | 3.2383 | 3.4203 | 3.5903 | 3.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W10A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4695 | 4695 | 4695 | 2822 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W10A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5156 | 5156 | 5156 | 5156 | 5156 | 3209 | 1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.65 | 3.65 | 3.65 | 3.65 | 3.65 | 3.65 | 3.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W12A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2821 | 2821 | 2821 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W12A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.18 | 3.18 | 3.18 | 3.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W12B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3622 | 3622 | 3622 | 3622 | 3622 | 3622 | 1675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W12B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W15A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 1016 | 1016 | 1016 | 1016 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W15A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W15B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692 | 1692 | 1692 | 1306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W15B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.77 | 2.77 | 2.77 | 2.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3965 | 3965 | 3965 | 3965 | 2167 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5256 | 5256 | 5256 | 5256 | 5256 | 3309 | 1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W18_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 963 | 963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W18_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 2794 | 2794 | 2794 | 922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3592 | 3592 | 3592 | 3592 | 3592 | 3592 | 3592 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W3A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1432 | 1432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W3A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W3B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565 | 2565 | 2565 | 2565 | 2565 | 2565 | 2323 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W3B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W5A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1962 | 1962 | 1962 | 1962 | 1962 | 1962 | 1962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W5A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W5B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012 | 2012 | 2012 | 2012 | 2012 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W5B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.43 | 3.43 | 3.43 | 3.43 | 3.43 | 3.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W9A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1015 | 1015 | 1015 | 1015 | 1015 | 1015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W9A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W9B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1886 | 1628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 12L_W9B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L Total | 12L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 23508 | 46444 | 44754 | 39979 | 33905 | 26573 | 17305 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L Total | 12L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 3.0807 | 3.1042 | 3.0715 | 3.0227 | 3.0153 | 3.0857 | 3.2037 | 3.1274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_E1_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9732 | 9732 | 9732 | 9732 | 7785 | 5763 | 3965 | 2018 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_E1_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W1_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2083 | 2083 | 2083 | 2083 | 2083 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W1_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W11A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 973 | 973 | 973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W11A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.47 | 2.47 | 2.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W11B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910 | 1910 | 1910 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W11B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.26 | 2.26 | 2.26 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W12A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3268 | 3268 | 3268 | 3268 | 3268 | 3268 | 3268 | 3268 | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W12A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W12B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4139 | 4139 | 4139 | 4139 | 4139 | 4139 | 4139 | 2341 | 543 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W12B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3398 | 3398 | 3398 | 3398 | 3398 | 3398 | 3398 | 3398 | 1600 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3792 | 3792 | 3792 | 3792 | 3792 | 3792 | 3792 | 3792 | 1994 | 196 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W18A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527 | 527 | 527 | 527 | 527 | 527 | 527 | 527 | 527 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W18A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W18B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621 | 621 | 621 | 621 | 621 | 621 | 621 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W18B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5015 | 5015 | 5015 | 5015 | 5015 | 2993 | 1195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 3.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5257 | 5257 | 5257 | 5257 | 5257 | 3235 | 1437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W5_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734 | 734 | 734 | 734 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W5_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.27 | 3.27 | 3.27 | 3.27 | 3.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W6_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4417 | 4417 | 4417 | 4417 | 4335 | 2537 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 12L_A_W6_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A Total | 12L_A Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2083 | 22821 | 27238 | 27238 | 30121 | 29495 | 34333 | 24370 | 18353 | 15816 | 15745 | 15745 | 15745 | 12149 | 5285 | 196 | 0 | 0 | 0 | 0 | 0
12L_A Total | 12L_A Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 2.7332 | 2.9126 | 2.9126 | 2.857 | 2.7547 | 2.5296 | 2.4168 | 2.1925 | 2.1313 | 2.131 | 2.131 | 2.131 | 2.1802 | 2.2259 | 2.25 | 0 | 0 | 0 | 0 | 0
13L | 13L_E1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21435 | 21435 | 21435 | 21435 | 21435 | 21435 | 19488 | 17616 | 15744 | 13946 | 12148 | 10350 | 8478 | 6531 | 4584 | 2712 | 765 | 2 | 2 | 2 | 2
13L | 13L_E1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09
13L | 13L_E1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22805 | 22805 | 22805 | 22805 | 22805 | 22805 | 20858 | 18911 | 17038 | 15165 | 13367 | 11569 | 9771 | 7898 | 5951 | 4004 | 2131 | 184 | 0 | 0 | 0 | 0
13L | 13L_E1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 0 | 0 | 0 | 0 | 0
13L | 13L_W10_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3629 | 3629 | 3629 | 3629 | 3629 | 3629 | 3629 | 3629 | 1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W10_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W12_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4238 | 4238 | 4238 | 4238 | 4238 | 4238 | 4238 | 2291 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W12_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6219 | 6219 | 6219 | 6219 | 6219 | 4777 | 2830 | 883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5043 | 5043 | 5043 | 5043 | 5043 | 5043 | 3096 | 1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6532 | 6532 | 6532 | 6532 | 4734 | 2787 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5841 | 5841 | 5841 | 5841 | 5841 | 3894 | 1947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748 | 1748 | 1748 | 1748 | 1748 | 1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450 | 2450 | 2450 | 2450 | 2450 | 2450 | 2450 | 2450 | 2450 | 578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 2.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1702 | 1702 | 1702 | 1702 | 1702 | 1702 | 1702 | 1702 | 1702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 3.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 2.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727 | 1727 | 1727 | 1727 | 1727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L | 13L_W9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L Total | 13L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63284 | 84719 | 84719 | 84719 | 82921 | 75858 | 64375 | 51853 | 42330 | 32837 | 27313 | 23717 | 20121 | 16376 | 12482 | 8588 | 4843 | 949
13L Total | 13L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7154 | 2.5571 | 2.5571 | 2.5571 | 2.5675 | 2.586 | 2.5582 | 2.5328 | 2.4478 | 2.2921 | 2.2515 | 2.251 | 2.2503 | 2.2492 | 2.2473 | 2.2439 | 2.2352 | 2.154
13L_A | 13L_A_E1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17277 | 17277 | 17277 | 17277 | 17277 | 17277 | 17277 | 17277 | 15405 | 13533 | 11735 | 9937 | 8139 | 6267 | 4320 | 2373 | 501 | 0
13L_A | 13L_A_E1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 3.34 | 0
13L_A | 13L_A_E1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14279 | 14279 | 14279 | 14279 | 14279 | 14279 | 14279 | 14279 | 14279 | 12406 | 10608 | 8810 | 7012 | 5139 | 3192 | 1245 | 0 | 0
13L_A | 13L_A_E1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0
13L_A | 13L_A_E4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7464 | 7464 | 7464 | 7464 | 7464 | 7464 | 5517 | 3570 | 1698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 2.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7025 | 7025 | 7025 | 7025 | 5227 | 3280 | 1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.31 | 3.31 | 3.31 | 3.31 | 3.31 | 3.31 | 3.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E5A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 767 | 767 | 767 | 767 | 767 | 767 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E5A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E5B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1835 | 1835 | 1835 | 1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_E5B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.51 | 3.51 | 3.51 | 3.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W10A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4309 | 4309 | 4309 | 4309 | 4309 | 2982 | 1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W10A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W10B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5188 | 5188 | 5188 | 3241 | 1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W10B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.03 | 2.03 | 2.03 | 2.03 | 2.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W12A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4897 | 4897 | 4897 | 2950 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W12A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.03 | 3.03 | 3.03 | 3.03 | 3.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W12B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4776 | 4776 | 4776 | 4776 | 2829 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W12B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W14A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3020 | 3020 | 3020 | 3020 | 3020 | 3020 | 3020 | 1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W14A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W14B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 2490 | 2490 | 2490 | 2490 | 2490 | 2490 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W14B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W16A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1324 | 1324 | 1324 | 1324 | 1324 | 1324 | 1324 | 1324 | 592 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W16A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W16B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3249 | 3249 | 3249 | 3249 | 3249 | 3249 | 3249 | 3249 | 1451 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W16B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7533 | 7533 | 7533 | 7533 | 7533 | 5586 | 3639 | 1692 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
13L_A | 13L_A_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72 | 3.72
13L_A | 13L_A_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6924 | 6924 | 6924 | 6924 | 6924 | 6924 | 6924 | 6924 | 5052 | 3180 | 1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W6A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3227 | 3227 | 3227 | 3227 | 3227 | 3227 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W6A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W6B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052 | 3052 | 3052 | 3052 | 3052 | 3052 | 3052 | 3052 | 3052 | 3052 | 1254 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W6B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W8_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2653 | 2653 | 2653 | 2653 | 2653 | 2653 | 2258 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W8_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W9_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2616 | 2616 | 2616 | 2616 | 818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | 13L_A_W9_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A Total | 13L_A Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70164 | 71999 | 84325 | 91159 | 100309 | 91815 | 80133 | 67962 | 57507 | 45624 | 32652 | 22590 | 16604 | 11408 | 7514 | 3620 | 503 | 2
13L_A Total | 13L_A Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5185 | 3.5183 | 3.4714 | 3.4859 | 3.2921 | 3.2778 | 3.278 | 3.3141 | 3.3641 | 3.4315 | 3.4444 | 3.4571 | 3.5257 | 3.6239 | 3.6077 | 3.5569 | 3.3415 | 3.72
14L | 14L_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4168 | 4168 | 4168 | 4168 | 4168 | 4168 | 4168 | 2370 | 572 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 3.59 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4764 | 4764 | 4764 | 4764 | 4764 | 4764 | 4764 | 2966 | 1168 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 2274 | 2274 | 2274 | 2274 | 2274 | 2274 | 2274 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2848 | 2848 | 2848 | 2848 | 2848 | 2848 | 1589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L | 14L_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L Total | 14L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5122 | 5122 | 5122 | 14054 | 14054 | 14054 | 12795 | 11206 | 9333 | 8932 | 5336 | 1740 | 0 | 0 | 0 | 0 | 0 | 0
14L Total | 14L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.7319 | 3.7319 | 3.7319 | 3.7085 | 3.6714 | 3.6114 | 3.5953 | 3.5956 | 3.5967 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W1A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5705 | 5705 | 5705 | 5705 | 5705 | 5705 | 5393 | 3595 | 1797 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W1A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 3.81 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W1B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6045 | 6045 | 6045 | 6045 | 6045 | 6045 | 6045 | 6045 | 4247 | 2449 | 576 | 0 | 0 | 0 | 0
14L_A | 14L_A_W1B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 0 | 0 | 0 | 0
14L_A | 14L_A_W4A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6602 | 6602 | 6602 | 6602 | 6602 | 6602 | 4730 | 2858 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W4A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W4B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6736 | 6736 | 6736 | 6736 | 6736 | 6736 | 4864 | 2992 | 1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W4B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.97 | 1.97 | 1.97 | 1.97 | 1.97 | 1.97 | 1.97 | 1.97 | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W7A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W7A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W7B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203 | 1203 | 1203 | 1203 | 1203 | 1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W7B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 3.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W8A_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4389 | 4389 | 4389 | 4389 | 4389 | 4389 | 4389 | 3379 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W8A_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W8B_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4841 | 4841 | 4841 | 4841 | 3355 | 1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 14L_A_W8B_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A Total | 14L_A Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9831 | 11034 | 24372 | 30417 | 34636 | 32689 | 31281 | 29068 | 23451 | 17600 | 13692 | 7842 | 4246 | 576 | 0 | 0 | 0 | 0
14L_A Total | 14L_A Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.236 | 2.4185 | 2.1433 | 2.4348 | 2.6679 | 2.691 | 2.7095 | 2.6862 | 2.8682 | 3.1119 | 3.4103 | 3.7017 | 3.6946 | 3.61 | 0 | 0 | 0 | 0
15L | 15L_W1_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5783 | 5783 | 5783 | 5783 | 5783 | 5783 | 5783 | 5783 | 3985 | 2112 | 165 | 0 | 0 | 0
15L | 15L_W1_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 0 | 0 | 0
15L | 15L_W10_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9962 | 9962 | 9962 | 9962 | 9962 | 8015 | 6068 | 4121 | 2249 | 377 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
15L | 15L_W10_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97
15L | 15L_W8_STP | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2589 | 2589 | 2589 | 2589 | 791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15L | 15L_W8_STP | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15L Total | 15L Total | Diluted_Stoping_Tonnes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12551 | 12551 | 12551 | 12551 | 16536 | 13798 | 11851 | 9904 | 8032 | 6160 | 5786 | 5786 | 3988 | 2115 | 168 | 3 | 3 | 3
15L Total | 15L Total | Au_dil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.97 | 3.97 | 3.97 | 3.97 | 3.3895 | 3.2743 | 3.16 | 3.0007 | 2.7748 | 2.4116 | 2.3109 | 2.3109 | 2.3112 | 2.3124 | 2.3396 | 3.97 | 3.97 | 3.97

## Developed Metres Schedule
| 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01
1L |  | 37 | 32 | 29 | 29 | 31 | 32 | 35 | 34 | 36 | 36 | 35 | 34 | 36 | 33 | 34 | 35 | 33 | 36 | 38 | 34 | 36 | 32 | 31 | 37 | 38 | 32 | 29 | 35 | 34 | 34 | 30 | 13
3L |  | 107 | 125 | 115 | 64 | 99 | 103 | 114 | 59 | 3 | 0 | 0 | 0 | 0 | 0
4L |  | 67 | 4 | 0 | 0 | 0 | 0 | 0
5L |  | 80 | 174 | 65 | 38 | 76 | 86 | 104 | 91 | 117 | 124 | 77 | 60 | 46 |  |  | 0 | 0 | 0
6L |  | 367 | 150 | 122 | 81 | 50 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L_A |  |  | 132 | 196 | 99 | 109 | 148 | 149 | 82 | 91 | 70 | 54 | 40 | 49 | 39 | 25 | 0 | 0
7L |  |  | 68 | 83 | 320 | 270 | 200 | 158 | 170 | 168 | 170 | 176 | 114 | 70 | 0 | 0 | 0 | 0 | 0
8L |  |  | 60 | 204 | 326 | 383 | 411 | 383 | 267 | 207 | 222 | 219 | 193 | 140 | 61 | 0 | 0 | 0 | 0 | 0
9L |  |  |  | 55 | 53 | 59 | 102 | 109 | 149 | 213 | 196 | 199 | 244 | 269 | 570 | 548 | 309 | 69 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.5L |  |  |  |  | 34 | 10 |  |  |  | 16 | 45 | 5
10L |  |  |  |  | 97 | 66 | 30 | 120 | 104 | 202 | 247 | 211 | 184 | 272 | 69 | 201 | 495 | 475 | 284 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | [10 empty] | 18 | 21 |  | 9 | 25 | 51 | 53 | 241 | 531 | 694 | 349 | 157 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | [7 empty] | 12 | 22 | 12 |  | 12 | 80 | 125 | 90 | 64 | 64 | 31 | 50 | 219 | 396 | 438 | 457 | 236 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.5L | [15 empty] | 20 | 36 | 22 | 34
12L | [14 empty] | 14 | 53 | 42 | 16 |  |  | 40 | 245 | 379 | 532 | 262 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | [16 empty] | 91 | 75 | 34 | 35 | 31 | 34 | 35 | 54 | 154 | 254 | 235 | 111 | 93 | 71 | 164 | 183 | 152 | 141 | 61 | 8 |  |  | 0 | 0 | 0 | 0
13L | [17 empty] | 3 | 68 | 116 | 69 | 85 | 49 | 94 | 313 | 381 | 271 | 197 | 184 | 126 | 95 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13L_A | [19 empty] | 49 | 109 | 105 | 87 | 65 | 91 | 174 | 265 | 269 | 297 | 412 | 398 | 349 | 273 | 220 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.5L | [29 empty] | 8 | 20
14L | [21 empty] | 19 | 35 | 33 | 35 | 51 | 102 | 114 | 160 | 68 | 83 | 150 | 86 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | [22 empty] | 52 | 57 | 43 | 32 | 31 | 152 | 157 | 151 | 215 | 258 | 144 | 87 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15L | [8 empty] | 16 | 17 | 18 | 16 | 16 | 17 | 15 | 16 | 16 | 16 | 17 | 18 | 16 | 17 | 35 | 33 | 57 | 43 | 51 | 112 | 126 | 132 | 53 | 33 | 52 | 51 | 44 | 51 | 33 | 10 | 0 |  | 0 | 0 | 0 | 0
Grand Total | 0 | 658 | 745 | 869 | 1141 | 1153 | 1119 | 1184 | 994 | 1082 | 1146 | 1025 | 965 | 1033 | 916 | 1012 | 1141 | 981 | 1062 | 1170 | 1044 | 1136 | 1198 | 1135 | 1069 | 1035 | 987 | 984 | 1052 | 1002 | 1062 | 1006 | 720 | 500 | 150 | 59 | 33 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | time axis 2025-01-01 to 2029-04-01
|  |  | 10.5L | 2025-03-01: 8; 2025-04-01: 20; 2025-05-01: 12; 2025-06-01: 9; 2025-07-01: 17; 2025-08-01: 13; 2025-09-01: 10; 2025-10-01: 15; 2025-11-01: 1 | 105
|  |  | 10L | 2025-03-01: 12; 2025-04-01: 36; 2025-05-01: 404; 2025-06-01: 629; 2025-07-01: 473; 2025-08-01: 378; 2025-09-01: 401; 2025-10-01: 424; 2025-11-01: 436; 2025-12-01: 504; 2026-01-01: 566; 2026-02-01: 320; 2026-03-01: 196; 2026-04-01: 128; 2026-05-01: 50; 2026-06-01: 12; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0 | 4969
|  |  | 11L | 2027-01-01: 816; 2027-02-01: 692; 2027-03-01: 408; 2027-04-01: 206; 2027-05-01: 60; 2027-06-01: 6; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0 | 2187
|  |  | 11L_A | 2027-01-01: 333; 2027-02-01: 354; 2027-03-01: 417; 2027-04-01: 392; 2027-05-01: 405; 2027-06-01: 259; 2027-07-01: 127; 2027-08-01: 44; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0 | 2331
|  |  | 12.5L | 2027-01-01: 111 | 111
|  |  | 12L | 2027-01-01: 802; 2027-02-01: 525; 2027-03-01: 203; 2027-04-01: 72; 2027-05-01: 43; 2027-06-01: 0; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0 | 1646
|  |  | 12L_A | 2027-01-01: 183; 2027-02-01: 155; 2027-03-01: 101; 2027-04-01: 149; 2027-05-01: 181; 2027-06-01: 171; 2027-07-01: 76; 2027-08-01: 68; 2027-09-01: 35; 2027-10-01: 34; 2027-11-01: 117; 2027-12-01: 145; 2028-01-01: 125; 2028-02-01: 140; 2028-03-01: 97; 2028-04-01: 44; 2028-05-01: 38; 2028-06-01: 94; 2028-07-01: 59; 2028-08-01: 2 | 2015
|  |  | 13L | 2027-01-01: 671; 2027-02-01: 434; 2027-03-01: 264; 2027-04-01: 279; 2027-05-01: 167; 2027-06-01: 121; 2027-07-01: 71; 2027-08-01: 43; 2027-09-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0; 2029-02-01: 0; 2029-03-01: 0; 2029-04-01: 0 | 2051
|  |  | 13L_A | 2027-01-01: 534; 2027-02-01: 516; 2027-03-01: 359; 2027-04-01: 254; 2027-05-01: 295; 2027-06-01: 234; 2027-07-01: 158; 2027-08-01: 144; 2027-09-01: 180; 2027-10-01: 154; 2027-11-01: 159; 2027-12-01: 121; 2028-01-01: 72; 2028-02-01: 26; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0 | 3205
|  |  | 14.5L | 2027-01-01: 28; 2027-02-01: 1 | 29
|  |  | 14L | 2027-01-01: 294; 2027-02-01: 187; 2027-03-01: 88; 2027-04-01: 40; 2027-05-01: 31; 2027-06-01: 59; 2027-07-01: 118; 2027-08-01: 93; 2027-09-01: 26; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0 | 937
|  |  | 14L_A | 2027-01-01: 455; 2027-02-01: 201; 2027-03-01: 112; 2027-04-01: 79; 2027-05-01: 99; 2027-06-01: 152; 2027-07-01: 152; 2027-08-01: 96; 2027-09-01: 39; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0 | 1385
|  |  | 15L | 2027-01-01: 382; 2027-02-01: 199; 2027-03-01: 126; 2027-04-01: 81; 2027-05-01: 43; 2027-06-01: 47; 2027-07-01: 41; 2027-08-01: 22; 2027-09-01: 23; 2027-10-01: 23; 2027-11-01: 23; 2027-12-01: 22; 2028-01-01: 22; 2028-02-01: 22; 2028-03-01: 22; 2028-04-01: 22; 2028-05-01: 22; 2028-06-01: 23; 2028-07-01: 23; 2028-08-01: 22; 2028-09-01: 19 | 1230
|  |  | 1L | 37 | 32 | 29 | 29 | 32 | 29 | 38 | 33 | 35 | 37 | 35 | 34 | 37 | 33 | 33 | 35 | 33 | 37 | 38 | 34 | 37 | 39 | 36 | 35 | 36 | 29 | 32 | 35 | 33 | 30 | 24 | 0 | 0 | 0 | [18 empty] | 1048
|  |  | 3L | 2025-01-01: 107; 2025-02-01: 125; 2025-03-01: 115; 2025-04-01: 121; 2025-05-01: 68; 2025-06-01: 27; 2025-07-01: 26; 2025-08-01: 24; 2025-09-01: 15; 2025-10-01: 1; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0 | 629
|  |  | 4L | 2025-01-01: 67; 2025-02-01: 2; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0 | 69
|  |  | 5L | 2025-01-01: 80; 2025-02-01: 174; 2025-03-01: 65; 2025-04-01: 15; 2025-05-01: 0; 2025-06-01: 4; 2025-07-01: 27; 2025-08-01: 89; 2025-09-01: 102; 2025-10-01: 113; 2025-11-01: 107; 2025-12-01: 118; 2026-01-01: 117; 2026-02-01: 75; 2026-03-01: 27; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0 | 1112
|  |  | 6L | 2025-01-01: 367; 2025-02-01: 150; 2025-03-01: 122; 2025-04-01: 10; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 29; 2025-09-01: 40; 2025-10-01: 21; 2025-11-01: 54; 2025-12-01: 34; 2026-01-01: 6; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0 | 833
|  |  | 6L_A | 2025-02-01: 132; 2025-03-01: 196; 2025-04-01: 226; 2025-05-01: 108; 2025-06-01: 75; 2025-07-01: 84; 2025-08-01: 72; 2025-09-01: 88; 2025-10-01: 104; 2025-11-01: 81; 2025-12-01: 60; 2026-01-01: 85; 2026-02-01: 76; 2026-03-01: 57; 2026-04-01: 80; 2026-05-01: 55; 2026-06-01: 33; 2026-07-01: 3; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0 | 1617
|  |  | 7L |  | 68 | 66 | 93 | 75 | 54 | 41 | 25 | 26 | 35 | 25 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | [6 empty] | 512
|  |  | 8L |  | 60 | 204 | 343 | 288 | 112 | 180 | 186 | 195 | 186 | 155 | 161 | 232 | 278 | 308 | 316 | 289 | 307 | 276 | 181 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 4302
|  |  | 9L | 2025-03-01: 55; 2025-04-01: 61; 2025-05-01: 35; 2025-06-01: 54; 2025-07-01: 192; 2025-08-01: 108; 2025-09-01: 122; 2025-10-01: 138; 2025-11-01: 104; 2025-12-01: 42; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0 | 911
|  |  | Grand Total | 658 | 743 | 871 | 956 | 1022 | 992 | 1078 | 956 | 1037 | 1075 | 998 | 958 | 1043 | 782 | 621 | 560 | 428 | 389 | 317 | 215 | 80 | 39 | 36 | 35 | 4646 | 3294 | 2109 | 1586 | 1359 | 1079 | 766 | 511 | 303 | 211 | 299 | 288 | 219 | 188 | 118 | 65 | 60 | 118 | 83 | 24 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33234

## Graphs Input
 | time axis 2024-06-01 to 2028-10-01
1L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3073 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13487 | 10454 | 7758 | 20887 | 15832 | 12156 | 10358 | 8486 | 6688 | 4890 | 7156 | 5358 | 2988 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3L | 0 | 0 | 0 | 0 | 0 | 11200 | 23802 | 23144 | 18748 | 11933 | 6130 | 1991 | 3362 | 6344 | 20965 | 33900 | 29703 | 23405 | 17339 | 11721 | 6329 | 1424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4L | -10323 | 0 | 0 | 0 | 0 | 0 | 8489 | 5456 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5L | 0 | 0 | 0 | 0 | 0 | 2149 | 351 | 5764 | 4225 | 14201 | 9356 | 3144 | 0 | 3267 | 6855 | 3439 | 6514 | 3225 | 11503 | 15134 | 15134 | 15134 | 9516 | 4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6L | 0 | 0 | 0 | 0 | 0 | 0 | 61161 | 48645 | 40685 | 71629 | 62856 | 59768 | 53309 | 41519 | 32848 | 26773 | 20707 | 15089 | 9697 | 4430 | 1846 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
6L_A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1007 | 0 | 6356 | 4752 | 15886 | 11391 | 6987 | 17447 | 12766 | 11103 | 7381 | 4797 | 4291 | 1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58600 | 54293 | 46319 | 37113 | 32945 | 29450 | 16211 | 7930 | 2536 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
8L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38606 | 38599 | 36549 | 40759 | 41692 | 31268 | 22028 | 10298 | 3964 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2818 | 14319 | 17367 | 87789 | 84587 | 75297 | 54024 | 46095 | 41928 | 37884 | 34139 | 30543 | 26798 | 23202 | 19606 | 16986 | 15188 | 13241 | 11219 | 9421 | 7474 | 5527 | 3580 | 1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7536 | 7536 | 75280 | 75280 | 72592 | 102099 | 115295 | 115301 | 95957 | 73823 | 57007 | 49040 | 41848 | 34358 | 27166 | 20244 | 16093 | 12497 | 8603 | 4559 | 2139 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61831 | 77644 | 92101 | 76275 | 58892 | 42044 | 28739 | 21255 | 15283 | 9889 | 5626 | 3476 | 1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11L_A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3401 | 11118 | 30484 | 39908 | 38653 | 36268 | 30874 | 20357 | 10306 | 3491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 23508 | 46444 | 44754 | 39979 | 33905 | 26573 | 17305 | 4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12L_A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2083 | 22821 | 27238 | 27238 | 30121 | 29495 | 34333 | 24370 | 18353 | 15816 | 15745 | 15745 | 15745 | 12149 | 5285 | 196 | 0 | 0 | 0 | 0 | 0 | 0
13L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63284 | 84719 | 84719 | 84719 | 82921 | 75858 | 64375 | 51853 | 42330 | 32837 | 27313 | 23717 | 20121 | 16376 | 12482 | 8588 | 4843 | 949 | 0
13L_A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70164 | 71999 | 84325 | 91159 | 100309 | 91815 | 80133 | 67962 | 57507 | 45624 | 32652 | 22590 | 16604 | 11408 | 7514 | 3620 | 503 | 2 | 0
14L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5122 | 5122 | 5122 | 14054 | 14054 | 14054 | 12795 | 11206 | 9333 | 8932 | 5336 | 1740 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14L_A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9831 | 11034 | 24372 | 30417 | 34636 | 32689 | 31281 | 29068 | 23451 | 17600 | 13692 | 7842 | 4246 | 576 | 0 | 0 | 0 | 0 | 0
15L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12551 | 12551 | 12551 | 12551 | 16536 | 13798 | 11851 | 9904 | 8032 | 6160 | 5786 | 5786 | 3988 | 2115 | 168 | 3 | 3 | 3 | 0
Grade | 1.56 | 1.77 | 2.27 | 1.49 | 1.82 | 1.98 | 2.15 | 2.13 | 1.97 | 2.12 | 2.46 | 2.58 | 2.55 | 2.4 | 2.48 | 2.66 | 2.71 | 2.62 | 2.46 | 2.43 | 2.69 | 2.82 | 2.93 | 2.83 | 2.86 | 2.75 | 2.63 | 2.64 | 2.3 | 2.32 | 2.33 | 2.33 | 2.43 | 2.51 | 2.49 | 2.58 | 2.75 | 2.9 | 2.82 | 2.84 | 2.96 | 2.93 | 2.84 | 2.88 | 2.92 | 2.93 | 2.88 | 3 | 2.87 | 2.94 | 2.86 | 2.38 | 2.16
| -10323 | 0 | 0 | 0 | 0 | 13349 | 93803 | 83009 | 66193 | 98770 | 78342 | 71259 | 64496 | 68067 | 72059 | 168305 | 167263 | 137353 | 135050 | 123657 | 178423 | 151737 | 189526 | 197310 | 204279 | 179783 | 211645 | 217687 | 213946 | 202606 | 205061 | 198870 | 189642 | 164090 | 297974 | 295361 | 291842 | 291802 | 286068 | 254237 | 221782 | 189322 | 158109 | 126902 | 96932 | 66964 | 45159 | 30479 | 20168 | 12215 | 5353 | 958 | 0